## Master Build v206
Component | ID / Path | Status | Version | Last Changed | Notes
WORKFLOWS
GDA.api.launchpad | GrbSQxeJs7ag6zXx | ACTIVE | S-205 | 2026-05-05 | AN-1 + incumbent_themes integrated; 103 PURSUE / 70 EVAL
GDA.api.pipeline | f4PLgyzEu0tj3R5Y | ACTIVE | S-205 | 2026-05-05 | 100-row table
GDA.dev.deploy | 8GnGxnBL9TJjj1i2 | ACTIVE | S-206 | 2026-05-05 | versionCounter 942; continueOnFail added to Notify TG Deploy; SSH expr fix live
GDA.util.gist-update | t2209zk3c9x0OS9S | ACTIVE | S-206 | 2026-05-05 | PATCH Gist credential fixed: genericCredentialType/httpHeaderAuth; Gist updated 16:11:35 UTC
GDA.util.ssh-read-file | IcD4K740vpWSIuaZ | ACTIVE | S-205 | 2026-05-05 | Auth guard: allowed prefixes; versionCounter 764
GDA.cron.learning-engine | fZpqchmmPnqAmiMq | ACTIVE | S-205 | 2026-05-05 | 12 weights calibrated 2026-05-05 02:48:36 UTC
GDA.api.morning-briefing | YIvCdrOgF1LGmFNL | ACTIVE | S-204 | 2026-05-04 | Canonical morning briefing
GDA.api.capture-plan | QgperN6cuOpfnb09 | ACTIVE | S-204 | 2026-05-04 | Capture plan generator
GDA.api.ingest (FROZEN) | MJapg8dGkvEzLn0K | FROZEN | — | — | DO NOT TOUCH
Frozen WF 1 | 1G4gw4N7DFtVZKF7 | FROZEN | — | — | DO NOT TOUCH
Frozen WF 2 | NQmaj5nu4TBQxBgD | FROZEN | — | — | DO NOT TOUCH
FRONTEND
gda.csr-llc.tech | n8n-envision-gda-frontend-1 | LIVE | v206 | 2026-05-05 | Nginx/alpine; Defense palette; DEPLOY_COMPLETE_1777997604
QACenterPage.jsx | /opt/gda-command/src/components/pages/ | PATCHED | S-206 | 2026-05-05 | export default QACenter appended; file was 70 lines (truncated), now complete
App.jsx | /opt/gda-command/src/App.jsx | LIVE | S-205 | 2026-05-05 | Backup: App.jsx.bak-s158-kpi; 2 duplicate key warnings (NASA, GSA) - non-blocking
INFRASTRUCTURE
VPS | 187.77.206.105 (Hostinger) | UP | — | 2026-05-05 | Post-maintenance recovery; 14.7GB free RAM; swap clear
n8n | n8n-envision-n8n-1 | UP | MCP 2.50.4 | 2026-05-05
Postgres | n8n-envision-postgres-1 | UP | pgvector/pg16 | 2026-05-05 | Port 5432; DB: n8n; User: n8n
Traefik | n8n-traefik-1 | UP | — | 2026-05-05 | TLS cert resolver clean
MCP | n8n-envision-mcp-1 | UP | 2.50.4 | 2026-05-05 | Was OOM-killed; recovered after pkill zombie n8n-mcp processes
DATABASE
gda_feedback | Postgres | LIVE | — | 2026-05-05 | 8 rows
gda_learned_weights | Postgres | LIVE | — | 2026-05-05 | 12 calibrated rows; updated 2026-05-05 02:48:36 UTC
CREDENTIALS
GDA Webhook Auth | 1pNPY36DDz49OtKL | ACTIVE | 2027 | S-206 | httpHeaderAuth; key: gda-api-2027-AWqjhbxDYNcyV1mr
GitHub Gist PAT | sKJFLNzetK86JnvO | ACTIVE | — | S-206 | httpHeaderAuth type (NOT githubApi); wired correctly in gist-update
VPS Root SSH Key | VqYFb1aRGJa8UfBc / NKOxLo5F81sRNPua | ACTIVE | — | —
OPEN ITEMS
S-206-01 | App.jsx duplicate keys | LOW | — | Carry | NASA + GSA duplicate keys in agency map — warnings only
S-206-02 | gda-tg-notify 500 | MED | — | Next session | Webhook returns 500 auth error; bypassed via continueOnFail on caller
HP-7 | nginx rate limiting | QUEUED | — | Next session | SSH VPS rate limit config