## Hardening Plan
# | Category | Finding | Count | Severity | What to Do | How to Fix (Technical) | Auto-Fix?
1 | Webhooks | Unauthenticated webhooks on ACTIVE workflows | 129 | HIGH (SECURITY) | Add HTTP Header Auth to every webhook. One shared secret (X-GDA-Key header) across all workflows. | n8n_manage_credentials(create httpHeaderAuth) → n8n_update_partial_workflow to set authentication:"headerAuth" on each webhook node. Batch scriptable. | YES
2 | Error Handling | 74 workflows have zero error handling | 74 | HIGH | Add Error Trigger workflow that catches failures, logs to Postgres, and alerts via Telegram/email. | Create one GDA.error.handler workflow with Error Trigger → Postgres INSERT → Telegram notification. Set as error workflow on all 74 workflows. | PARTIAL
3 | SQL Injection | 35 Postgres nodes with expressions in Query field without parameterization | 35 | HIGH (SECURITY) | Rewrite all 35 queries to use $1, $2 parameterized queries instead of string interpolation. | For each: move expression values to Query Parameters array. Change query from "WHERE id = {{$json.id}}" to "WHERE id = $1" with parameter [$json.id]. | NO
4 | SQL Injection | 229 Postgres nodes with no Query Parameters field used at all | 229 | MEDIUM | Audit each query. If it uses only static SQL with no user input, mark safe. If it interpolates, parameterize. | Priority: fix the 35 with expressions first. Then audit remaining 229 — many may be static and safe. | NO
5 | Credentials | 9 nodes with hardcoded emails/phone numbers in workflow JSON | 9 | MEDIUM | Move to environment variables or n8n credential store. Reference via expressions. | Replace hardcoded values with $env.ALERT_EMAIL, $env.ALERT_PHONE, etc. Add to .env file. | NO
6 | Credentials | 22 unused credentials stored in n8n | 22 | MEDIUM | Delete all unused credentials to reduce attack surface. | n8n_manage_credentials(action:"list") → identify unused → n8n_manage_credentials(action:"delete") for each. | YES
7 | Data Retention | 89 workflows retaining all execution data indefinitely | 89 | LOW | Configure global execution pruning: keep last 30 days max. Reduce storage and exposure. | n8n Settings → Executions → set pruneDataMaxAge=720 (30 days). Or per-workflow via settings. | NO
8 | Instance | n8n is 6 versions behind (v2.9.2 vs v2.14.2) | 1 | MEDIUM | Update n8n Docker image to latest stable. | cd ~/n8n-envision && update docker-compose.yml image tag → docker compose down → docker compose up -d. Test all E2E after. | NO
9 | Duplicates | 2 duplicate Stage Audit Logger workflows (both active) | 2 | LOW | Delete the older duplicate. Keep the latest. | n8n_delete_workflow for the older ID after confirming which is current. | YES
10 | Dead Workflows | ~15 INACTIVE/SUPERSEDED workflows still stored | 15 | LOW | Archive or delete superseded workflows (AI Decision Engine, Market Learning Pipeline, old black-hat, etc.) | Review each inactive workflow. Delete if superseded. Keeps instance clean. | NO

## Executive Summary
GDA COMMAND — Platform Maturity Assessment
Georgetown Defense Analytics ¦ Envision (OU3) ¦ April 2026
Scope: Capabilities + Gaps + Consolidation + Hardening + UX + Roadmap
PLATFORM STATE
148 | 110 | 420+ | $800M+ | 1,230 | 129 | 99 | 35
Workflows | Capabilities | Opps Tracked | Pipeline | Audit Findings | HIGH Severity | MEDIUM | SQL Injection Risk
SECURITY AUDIT RESULTS (Real Data — Run April 6, 2026)
Unauthenticated webhooks | 129 HIGH across 85+ workflows | Auto-fixable: add header auth to all webhooks in batch
No error handling | 74 workflows have zero error handling | Add Error Trigger nodes to catch failures silently
SQL injection exposure | 35 Postgres queries with unsanitized expressions, 229 without query parameters | Parameterize all SQL queries; use Query Parameters field
Hardcoded credentials | 9 nodes with hardcoded emails/phones in workflow data | Move to n8n credential store or environment variables
Excessive data retention | 89 workflows retaining all execution data | Configure execution pruning in n8n Settings
Outdated n8n instance | Running v2.9.2 — 6 versions behind (latest: v2.14.2) | Update n8n Docker image
22 unused credentials | Stored but not used in any workflow | Delete to reduce attack surface
THREE WORK STREAMS
1. HARDEN | Fix 129 unauthenticated webhooks, add error handling, parameterize SQL, update n8n. Protect what you built.
2. CONSOLIDATE | Merge fragmented workflows: 6 capture intel → 1, 5 comp intel → 1, 10 scanners → 1 master. Faster UX, less cost.
3. ENHANCE | Add RSS feeds, PGVector search, Telegram bot, email digests, doc auto-indexing. New capabilities on solid foundation.

## Consolidation Map
# | Cluster | Current Workflows | Count | Frontend Tab(s) Affected | Problem | Consolidation Target | API Calls Before → After | UX Impact | Priority
1 | Capture Intelligence | capture-intel, capture-intel-modules, capture-hub, capture-plan, ooda-loop, pwin-calculator | 6 | Capture Plan tab | Capture Plan tab makes 3-4 separate webhook calls. Each independently hits Postgres + Claude. 3-4x latency, 3-4x API cost. | GDA.api.capture-mega: single workflow with internal routing by action param (plan/intel/ooda/pwin/hub) | 4 calls → 1 call | Page loads 60% faster. One loading spinner instead of four. One error to handle instead of four. | HIGH
2 | Competitive Intel | competitor-watchlist, comp-intel 2, competitor-threat-score, competitor-field, incumbent-analysis | 5 | Comp Intel tab | 5 separate workflows all query the same competitor data. Each calls Claude independently. Redundant DB queries. | GDA.api.compintel-mega: single workflow, action param routes to watchlist/dashboard/threat/field/incumbent | 3-5 calls → 1 call | Comp Intel cards load in one shot. No more partial renders where some cards appear while others spin. | HIGH
3 | Opportunity Data | opp-tracker 2, opp-search, saved-opps, pipeline, launchpad-funnel, opp-classifier | 6 | Pipeline, Launchpad, Search | Frontend calls different endpoints for what is essentially "show pipeline filtered differently." Same Postgres table hit 6 ways. | GDA.api.pipeline-mega: single workflow with action param (list/search/saved/funnel/classify). One DB connection. | 2-3 calls → 1 call | Pipeline pages load faster. Consistent data — no stale cache mismatches between views. | HIGH
4 | Dashboard/Reporting | sitrep 2 (36 nodes!), daily-briefing, daily-brief, dashboard-intel 2, dashboard-intel-deep, ops-dashboard-data, intel-feed, trends, chart-generator, e2e-reports | 10 | Dashboard, SITREP | 10 workflows power the dashboard. Some overlap (daily-briefing vs daily-brief). SITREP at 36 nodes is a monolith. | Keep SITREP separate (complex). Merge dashboard-intel + dashboard-intel-deep + ops-dashboard-data + intel-feed into GDA.api.dashboard-mega. | 5-6 calls → 2 calls | Dashboard KPIs load as one unit. No more individual panels loading at different speeds. | MEDIUM
5 | Scheduled Scanners | broad-opp-search, dept-opp-sweep, on-ramp-scanner, forecast-ingest, dpc-forecast-scraper, dhs-industry-day-monitor, golden-dome-monitor, amendment-monitor, change-detector, pre-sam-monitor | 10 | Background (no UI) | 10 independent crons with 10 separate error handlers (or none — audit shows many have zero error handling). No coordination. Silent failures. | GDA.cron.master-scanner: one Schedule Trigger → calls each scan as sub-workflow in sequence. Unified error handling + completion log. | 10 crons → 1 cron | No UX change, but huge reliability gain. One place to check "did my overnight sweep complete?" One error log. | HIGH
6 | Document Intel | doc-ingest, batch.doc-ingest, doc-compare, rag-query | 4 | Doc Ingest, Compare | 4 separate workflows for document operations. Ingest has 2 versions (single + batch). RAG query is separate from ingest. | Keep doc-ingest and rag-query separate (different triggers). Merge batch.doc-ingest into doc-ingest with batch mode param. | Minimal change | Cleaner codebase. One ingest workflow handles single + batch. | LOW
7 | Relationships | relationship-tracker, relationships, contacts, teaming-finder, win-loss-db | 5 | Relationships tab | 5 separate CRUD workflows for related data. All hit same Postgres tables. | GDA.api.relationships-mega: single workflow with resource param (tracker/contacts/teaming/winloss). | 3 calls → 1 call | Relationships tab loads faster. Consistent data view. | LOW
8 | Financial | aop-tracker, aop-definitions, FY Revenue Calculator, nightly-fy-revenue-calc | 4 | Financial Bible tab | 4 workflows for financial data. Two revenue calculators (manual + nightly). | Merge aop-tracker + aop-definitions into GDA.api.financial-mega. Keep nightly calc as cron. | 2 calls → 1 call | Financial Bible tab loads as one unit. | LOW
9 | Dev/Test Utils | grep-appjsx, read-appjsx, ssh-read-file, e2e-test, workflow-mega-test, frontend-e2e | 6 | None (dev tools) | 6 developer utilities. Some overlap (grep vs read). Test workflows from specific sessions (s117). | Keep ssh-read-file as canonical. Delete session-specific test workflows. Consolidate grep + read. | No UI change | Cleaner workflow list. Less clutter. | LOW
10 | Dead/Superseded | AI Decision Engine [SUPERSEDED], Market Learning Pipeline [SUPERSEDED], ai-agent 2 (INACTIVE), general-chat (INACTIVE), capture-execution-suite (INACTIVE), challenge-ledger (INACTIVE), exit-manager (INACTIVE), opp-daily (INACTIVE), broad-opp-pull (INACTIVE), clear-stale-trade (INACTIVE) | 10 | None | 10 dead workflows consuming space and appearing in audit findings. Some have unauthenticated webhooks that are technically reachable. | DELETE all superseded/dead workflows. Remove from instance entirely. | No change | Reduces audit noise by ~30 findings. Cleaner instance. | MEDIUM

## Gap Analysis
# | Domain | What You Have | WHAT IS MISSING | Impact on You | Solution | Template Pattern | Priority
1 | Intel Feeds | GovTribe, DPC scraper, DHS/Golden Dome monitors | NO defense news RSS. No real-time SAM.gov. No news aggregation. | You find out about agency changes days late. Intel is reactive. | RSS Feed Trigger → Claude → email. Apify SAM.gov → webhook. | #5103, Apify SAM.gov | CRITICAL
2 | Semantic Search | RAG query but keyword-only. No vector embeddings. | Cannot ask "find C5ISR opportunities." Keyword match only. | 420+ opps and you cant search by concept. Connections invisible. | PGVector on existing Postgres. Zero new infrastructure. | #10157 (Agentic RAG) | CRITICAL
3 | SAM.gov Streaming | Pre-SAM monitor INACTIVE. Batch/daily only. | No real-time new opportunity detection. | Competitors with real-time alerts get first-mover advantage. | Apify SAM.gov → webhook. Or SAM.gov API on 15-min cron. | Apify SAM.gov Monitor | CRITICAL
4 | Mobile Access | Desktop web only at gda.csr-llc.tech. | NO mobile interface. No alerts on the go. | During travel/meetings — GDA is unreachable. You are blind. | Telegram Bot: private, free, instant. Voice notes → actions. | Telegram patterns | HIGH
5 | Doc Auto-Index | Manual trigger ingest only. | New RFPs sit in folders unindexed. | Drop RFP, forget to ingest, cant query it a week later. | Google Drive Trigger → chunk → embed into PGVector. | #2753 (94,941 views) | HIGH
6 | Competitor Web | GovTribe data only. No live web crawling. | Cannot monitor competitor press releases, hiring, capabilities. | Miss competitor strategic moves and partnerships. | Firecrawl — AI web scraping with structured extraction. | Firecrawl + Schedule | HIGH
7 | AI Chat Memory | chat-simple with no persistent memory. No multi-tool. | Every chat starts from zero. No cross-session context. | Repeat setup questions every session. AI has amnesia. | AI Agent + Postgres Chat Memory + PGVector + SQL tools. | #10157, #3414 | HIGH
8 | Live Web Research | Static Claude analysis. No real-time search. | Cannot query recent agency/program news during capture. | Capture intel based on stale data. Miss recent changes. | Perplexity node (core). Nightly research per active opp. | Perplexity (core) | MEDIUM
9 | Calendar Sync | No calendar integration at all. | No auto-created events for due dates or review gates. | Manual deadline tracking. Risk of missed dates. | Google Calendar — auto-create from capture milestones. | Google Calendar (core) | MEDIUM
10 | Email Digests | Daily briefing INACTIVE. No scheduled reports. | No passive intel delivery. Must log in to learn anything. | Zero passive consumption. You check or you miss it. | Schedule → Postgres → Claude → HTML → Gmail. | #10776 | MEDIUM
11 | Gov Portal Nav | SAM.gov via API only. No interactive portal automation. | Cannot navigate FPDS, SAM entity pages, JS-heavy portals. | Some data locked behind interactive portals. | Browserbase Agent for interactive sites. | Browserbase node | LOW
12 | Advanced Docs | No OCR. No scanned PDF handling. | Cannot process scanned RFPs or image-heavy docs. | Occasional scanned docs require manual rework. | PDF Vector — OCR, markdown, AI extraction. | PDF Vector node | LOW

## Master Roadmap
# | Phase | Stream | Action | Closes | What It Does For You | Days | Priority | Status
PHASE 0 — HARDEN FIRST (This Week)
1 | P0 | Harden | Batch-add webhook auth to all 129 endpoints | Security | Every webhook gets X-GDA-Key header auth. One script, 2 hours execution. Closes the biggest security hole. | 2 | CRITICAL | NOT STARTED
2 | P0 | Harden | Create unified error handler + attach to 74 workflows | Security | One GDA.error.handler catches all failures → logs to Postgres → Telegram alert. No more silent failures. | 3 | CRITICAL | NOT STARTED
3 | P0 | Harden | Parameterize top 35 SQL queries with expressions | Security | Eliminate SQL injection risk on the most exposed queries. Use $1 parameters. | 4 | HIGH | NOT STARTED
4 | P0 | Harden | Update n8n from v2.9.2 → v2.14.2 | Security | 6 versions of security patches, bug fixes, and performance improvements. | 1 | HIGH | NOT STARTED
5 | P0 | Harden | Delete 10 dead/superseded workflows + 22 unused credentials | Cleanup | Reduce attack surface. Eliminate 30+ audit findings. Cleaner instance. | 1 | MEDIUM | NOT STARTED
6 | P0 | Harden | Configure execution data pruning (30 day max) | Security | Stop accumulating execution data indefinitely. Closes 89 LOW findings. | 0.5 | MEDIUM | NOT STARTED
PHASE 1 — CONSOLIDATE + FIRST ENHANCEMENTS (Weeks 2-3)
7 | P1 | Consolidate | Merge 10 scanners → GDA.cron.master-scanner | Reliability | One cron, one error handler, one completion log. Know if your overnight sweep actually ran. | 3 | HIGH | NOT STARTED
8 | P1 | Consolidate | Merge 6 capture intel workflows → capture-mega | UX Speed | Capture Plan tab: 4 API calls → 1. Page loads 60% faster. | 4 | HIGH | NOT STARTED
9 | P1 | Consolidate | Merge 5 comp intel workflows → compintel-mega | UX Speed | Comp Intel tab: 5 calls → 1. Cards render together, not in random order. | 3 | HIGH | NOT STARTED
10 | P1 | Consolidate | Delete 10 dead workflows | Cleanup | Remove superseded/inactive clutter from instance. | 0.5 | MEDIUM | NOT STARTED
11 | P1 | Enhance | Morning Intel Briefing (RSS + Claude + Email) | Gap 1,10 | Defense news RSS → Claude classifies → email at 0600. Read with coffee. | 3 | CRITICAL | NOT STARTED
12 | P1 | Enhance | SAM.gov Real-Time Scanner | Gap 3 | New NAICS matches hit pipeline within 15 minutes. No manual checking. | 4 | CRITICAL | NOT STARTED
PHASE 2 — FOUNDATION (Weeks 3-4)
13 | P2 | Consolidate | Merge 6 opp data workflows → pipeline-mega | UX Speed | Pipeline/Launchpad: 3 calls → 1. Consistent data across all views. | 3 | HIGH | NOT STARTED
14 | P2 | Consolidate | Merge 4 dashboard workflows → dashboard-mega | UX Speed | Dashboard KPIs load as one unit instead of 5 separate panels. | 3 | MEDIUM | NOT STARTED
15 | P2 | Enhance | PGVector Semantic Search | Gap 2 | Ask "find all C5ISR opportunities" and get semantic matches. On YOUR Postgres. | 5 | CRITICAL | NOT STARTED
16 | P2 | Enhance | Agentic RAG Chatbot | Gap 2,7 | Multi-tool AI: vector + SQL + docs. Persistent memory across sessions. | 7 | HIGH | NOT STARTED
17 | P2 | Enhance | Telegram Bot | Gap 4 | YOUR private bot. Text "pipeline health" from phone. Approve bids with a tap. | 4 | HIGH | NOT STARTED
PHASE 3 — EXPANSION (Month 2)
18 | P3 | Enhance | Competitor Website Crawler (Firecrawl) | Gap 6 | Weekly crawl of competitor sites. Auto-update comp intel cards. | 5 | HIGH | NOT STARTED
19 | P3 | Enhance | Auto-Index Document Pipeline | Gap 5 | Drop RFP in Drive → queryable in 60 seconds. KB grows without effort. | 5 | HIGH | NOT STARTED
20 | P3 | Enhance | Perplexity Nightly Research | Gap 8 | Every night: active capture opps → Perplexity research → Daily Actions queue. | 4 | MEDIUM | NOT STARTED
21 | P3 | Enhance | Google Calendar Milestone Sync | Gap 9 | Proposal due dates auto-appear in Google Calendar. Mobile reminders. | 3 | MEDIUM | NOT STARTED
22 | P3 | Enhance | Embedded Chat Widget | Gap 7 | Chat bubble on gda.csr-llc.tech. Ask questions without clicking tabs. | 3 | MEDIUM | NOT STARTED
PHASE 4 — POLISH (Month 2-3)
23 | P4 | Enhance | Scheduled Email SITREP | Gap 10 | Weekly SITREP auto-generated and emailed. Zero effort. | 3 | MEDIUM | NOT STARTED
24 | P4 | Enhance | Capture Milestone Alerts (Telegram) | Gap 9 | Deadlines within 7/14/30 days → Telegram alerts. Never miss a due date. | 3 | MEDIUM | NOT STARTED
25 | P4 | Enhance | SMS Critical Failsafe (Twilio) | — | Emergency SMS for critical deadlines. Last-resort channel. | 2 | MEDIUM | NOT STARTED
26 | P4 | Enhance | n8n Quick-Entry Form | — | Bookmarked URL: drop opp URL, upload RFP. Faster than platform nav. | 2 | MEDIUM | NOT STARTED
27 | P4 | Harden | Parameterize remaining 229 SQL queries | Security | Full SQL injection hardening across all Postgres operations. | 5 | MEDIUM | NOT STARTED
PHASE 5 — ADVANCED (Month 3)
28 | P5 | Enhance | Browserbase Gov Portal Agent | Gap 11 | AI navigates interactive govt portals without APIs. | 5 | LOW | NOT STARTED
29 | P5 | Enhance | PDF Vector Doc Processing | Gap 12 | OCR scanned RFPs. Extract form fields. Handle image-heavy docs. | 3 | LOW | NOT STARTED
30 | P5 | Enhance | Autonomous Morning Loop | All | Master orchestrator at 0600: scan → classify → alert → report. | 3 | LOW | NOT STARTED
31 | P5 | Consolidate | Remaining merges (relationships, financial, dev utils) | Cleanup | Final cleanup pass. Merge remaining fragmented clusters. | 4 | LOW | NOT STARTED

## Effort Summary
Phase | Stream | Items | What You Get
Phase 0 | Harden | 6 | All 129 webhooks authenticated. Error handling on 74 workflows. Top 35 SQL queries parameterized. n8n updated. Dead workflows deleted. Data retention configured.
Phase 1 | Consolidate + Enhance | 6 | 3 mega-workflows (scanners, capture, comp intel). Morning briefing running. SAM.gov real-time scanner live.
Phase 2 | Consolidate + Enhance | 5 | 2 more mega-workflows (pipeline, dashboard). PGVector semantic search. RAG chatbot. Telegram bot on your phone.
Phase 3 | Enhance | 5 | Firecrawl competitor monitoring. Auto-indexing docs. Perplexity nightly research. Calendar sync. Embedded chat.
Phase 4 | Enhance + Harden | 5 | Email SITREPs. Milestone alerts. SMS failsafe. Quick-entry form. Remaining SQL hardening.
Phase 5 | Enhance + Consolidate | 4 | Browser automation. PDF OCR. Autonomous morning loop. Final cleanup.
TOTAL | — | 31 | Hardened, consolidated, and enhanced GDA Command. From 148 fragmented workflows to ~100 clean, secure, monitored workflows with mobile access, semantic search, and proactive intelligence.

## Current Capabilities
# | Domain | Capability | Workflow(s) | Active | Auth? | Error Handler?
1 | Opp Intel | Opportunity Tracker | opp-tracker 2 | Y | N | Y
2 | Opp Intel | Opportunity Search | opp-search | Y | N | N
3 | Opp Intel | Saved Opportunities | saved-opps / save-opp | Y | N | Y
4 | Opp Intel | GovTribe Feed | govwin-feed / govtribe-cache | Y | N | N
5 | Opp Intel | Broad Opp Search | broad-opp-search | Y | N | N
6 | Opp Intel | On-Ramp Scanner | on-ramp-scanner | Y | — | N
7 | Opp Intel | Dept Sweep | dept-opp-sweep | Y | N | Y
8 | Opp Intel | SAM Pre-Monitor | pre-sam-monitor | N | N | Y
9 | Opp Intel | Forecast Ingest | forecast-ingest | Y | N | N
10 | Opp Intel | DPC Forecast Scraper | dpc-forecast-scraper | Y | N | Y
11 | Opp Intel | DHS Industry Day | dhs-industry-day-monitor | Y | N | Y
12 | Opp Intel | Golden Dome Monitor | golden-dome-monitor | Y | N | N
13 | Opp Intel | Amendment Monitor | amendment-monitor | Y | — | Y
14 | Opp Intel | Change Detector | change-detector | Y | — | Y
15 | Opp Intel | Opp Cross-Wire | opp-cross-wire | Y | N | N
16 | Capture | Capture Plan (Shipley v2) | capture-plan | Y | N | Y
17 | Capture | Auto Capture Plans | auto-capture-plans | Y | — | Y
18 | Capture | Batch Capture Analysis | analyze-capture-plans | N | N | Y
19 | Capture | Capture Intelligence | capture-intel | Y | N | Y
20 | Capture | Capture Intel Modules | capture-intel-modules | Y | N | Y
21 | Capture | Capture Hub | capture-hub | Y | N | N
22 | Capture | OODA Loop | ooda-loop 2 | Y | N | Y
23 | Capture | PWin Calculator | pwin-calculator | Y | N | Y
24 | Capture | Opp Classifier | opp-classifier | Y | N | N
25 | Capture | Stage Promotion | opp-stage-promote | Y | — | N
26 | Capture | Auto Stage Progression | auto-stage-progression | Y | N | Y
27 | Comp Intel | Competitor Watchlist | competitor-watchlist | Y | N | Y
28 | Comp Intel | Comp Intel Dashboard | comp-intel 2 | Y | N | Y
29 | Comp Intel | Threat Score | competitor-threat-score | Y | N | Y
30 | Comp Intel | Field Analysis | competitor-field | Y | N | N
31 | Comp Intel | Weekly Scan | weekly-comp-scan | Y | — | N
32 | Comp Intel | Auto-Enrichment | Competitor Auto-Enrichment | Y | N | N
33 | Comp Intel | Incumbent Analysis | incumbent-analysis | Y | N | Y
34 | Proposal | Doc Ingest | doc-ingest / batch | Y | N | Y
35 | Proposal | Doc Compare | doc-compare | Y | N | N
36 | Proposal | RAG Query | rag-query | Y | N | N
37 | Proposal | Red Team | red-team | Y | N | Y
38 | Proposal | Black Hat | black-hat | Y | N | Y
39 | Proposal | Compliance Matrix | compliance-matrix | Y | N | Y
40 | Proposal | Clause Library | clause-library | Y | N | Y
41 | Financial | AOP Tracker | aop-tracker | Y | N | N
42 | Financial | IDIQ Tracker | idiq-tracker | Y | N | Y
43 | Financial | FY Revenue Calc | FY Revenue Auto-Calc | Y | N | N
44 | AI | Priority Score v2.1 | Priority Score v2.1 | Y | N | N
45 | AI | Smart Recommender | Smart Recommender | Y | N | N
46 | AI | Pattern Extractor | Pattern Extractor | Y | N | N
47 | AI | Daily Actions | daily-actions | Y | N | Y
48 | AI | Wargame Simulator | wargame | Y | N | N
49 | Reporting | SITREP (36 nodes) | sitrep 2 | Y | N | Y
50 | Reporting | Dashboard Intel | dashboard-intel 2 / deep | Y | N | Y
51 | Reporting | Chart Generator | chart-generator | Y | N | N
52 | Collab | Email Drafter | email-drafter | Y | N | Y
53 | Collab | Meeting Notes | meeting-notes 2 | Y | N | Y
54 | Relations | Relationship Tracker | relationship-tracker | Y | N | N
55 | Relations | Teaming Finder | teaming-finder | Y | N | N
56 | Platform | Deploy Pipeline | deploy | Y | N | Y
57 | Platform | Health Scan | health-scan | Y | N | N
58 | Platform | E2E Test (32/32) | e2e-test suites | Y | N | N
59 | Platform | Data Sync v2 | DataSync_v2 | Y | — | N
60 | Platform | Chat Simple | chat-simple | Y | N | N