## Hardening Plan
# | Category | Finding | Count | Severity | Action | Technical How-To | Auto-Fix? | Days
1 | Webhooks | Unauthenticated webhooks on ACTIVE workflows | 129 | HIGH (SECURITY) | Add X-GDA-Key header auth to every webhook. One shared secret across all. | n8n_manage_credentials(create httpHeaderAuth) → n8n_update_partial_workflow batch. Script runs in ~2hrs. | YES | 2
2 | Error Handling | Workflows with zero error handling | 74 | HIGH | Create GDA.error.handler: Error Trigger → log to Postgres → Telegram alert. Attach to all 74. | One handler workflow. Then set errorWorkflow on each via n8n_update_partial_workflow. Telegram notifies you of any failure. | PARTIAL | 3
3 | SQL Injection | Postgres queries with expressions in Query field | 35 | HIGH (SECURITY) | Rewrite to use $1 parameterized queries. Move expression values to Query Parameters array. | Change "WHERE id = {{$json.id}}" to "WHERE id = $1" with params [$json.id]. Requires manual review per query. | YES | ✅ S-136→S-142
4 | Task Runners | Heavy workflows (51-node export, 36-node SITREP, RAG) can timeout the main process | — | HIGH | Configure n8n Task Runners to isolate heavy execution in separate Docker containers. | Add N8N_RUNNERS_ENABLED=true to .env. Configure runner container in docker-compose.yml. Prevents main n8n from blocking. | YES | ✅ S-136
5 | SQL Queries | Postgres queries without Query Parameters field at all | 229 | MEDIUM | Audit each. If static SQL — mark safe. If interpolates user input — parameterize. | Priority: the 35 with expressions first (item 3). Remaining 229 are lower risk but should be reviewed over time. | NO | 5
6 | Credentials | Hardcoded emails/phone numbers in workflow JSON | 9 | MEDIUM | Move to $env variables or n8n credential store. | Replace with $env.ALERT_EMAIL, $env.ALERT_PHONE. Add to ~/n8n-envision/.env. Restart Docker. | NO | 1
7 | Credentials | Unused credentials stored in n8n | 22 | MEDIUM | Delete all unused credentials. | n8n_manage_credentials(list) → identify unused → delete each. | YES | ✅ S-137
8 | Instance | n8n 6 versions behind (v2.9.2 → v2.14.2) | 1 | MEDIUM | Update n8n Docker image. | Update image tag in docker-compose.yml → docker compose down → up -d. Run full E2E test after. | NO | 1
9 | Data Retention | Excessive execution data stored indefinitely | 89 | LOW | Configure global 30-day pruning. | n8n Settings → Executions → pruneDataMaxAge=720 hours. | NO | 0.5
10 | Dead Code | Duplicate Stage Audit Logger + 10 superseded/inactive workflows | 12 | LOW | Delete duplicates and superseded workflows. | n8n_delete_workflow for each. Removes ~30 audit findings. | YES | ✅ S-136
11 | HITL Governance | Red Team, SITREP, and bid decisions distribute without human approval | — | MEDIUM | Add Send-and-Wait approval step before distributing Red Team/SITREP outputs. | On SITREP workflow: after Claude generates report → Telegram Send-and-Wait → you approve/edit → then email/distribute. | YES | ✅ S-137–S-138
12 | Notifications | Telegram bot deployed — E2E, errors, deploy alerts + two-way chat | 3 | LOW | RESOLVED S-135

## Executive Summary
GDA COMMAND — Platform Maturity Assessment (Final)
Georgetown Defense Analytics ¦ Envision (OU3) ¦ April 6, 2026
Includes: Audit data, Gemini cross-validation, consolidation map, hardening plan, single-operator UX
PLATFORM STATE
148 | 110 | 420+ | $800M+ | 32/32 | 1,230 | 129 | 35
Workflows | Capabilities | Opps Tracked | Pipeline | E2E Pass Rate | Audit Findings | Unauth Webhooks | SQL Injection Risk
SECURITY AUDIT (Real scan — April 6, 2026)
129 unauthenticated webhooks | HIGH | Batch-add X-GDA-Key header auth via MCP
74 workflows with zero error handling | HIGH | Create GDA.error.handler + attach to all
35 SQL queries with unsanitized expressions | HIGH | Parameterize with $1/$2 query parameters
229 SQL queries without query params field | MEDIUM | Audit + parameterize critical ones
n8n v2.9.2 — 6 versions behind | MEDIUM | Update Docker image to v2.14.2
22 unused credentials stored | MEDIUM | Delete to reduce attack surface
89 workflows with excessive data retention | LOW | Configure 30-day execution pruning
GEMINI CROSS-VALIDATION NOTES
Gemini: "43% pass rate" on GDA tests | WRONG. Our E2E tests are 32/32 (100%). Gemini fabricated this metric.
Gemini: "Task Runner node" | PARTIALLY RIGHT. Task Runners are an n8n 2.0 infra config, not a node. But the concept is valid — isolate heavy RAG/doc workflows.
Gemini: "SQL Visualizer" as separate template | REDUNDANT. The Agentic RAG chatbot already does this — AI Agent + Postgres Tool generates charts.
Gemini: "MCP Server Integration" as new add | ALREADY HAVE IT. Our n8n MCP is at mcp.csr-llc.tech. Claude connects every session.
Gemini: "Deep Research Agent" (Template #2883) | VALID ADD. 21,345 views. Autonomous multi-step research via Perplexity. Better than single-shot queries.
Gemini: "Human-in-the-Loop" pattern | VALID ADD. Not a node — its a design pattern. Use Send-and-Wait on Telegram for SITREP/Red Team approvals.
Gemini: "AI Vision scraping" for govt portals | VALID ALTERNATIVE. More resilient than Firecrawl for sites that change layouts. Use Gemini Vision to "read" the page.
FOUR WORK STREAMS
1. HARDEN | Fix 129 unauth webhooks, 35 SQL injections, add error handling, update n8n, configure Task Runners.
2. CONSOLIDATE | Merge fragmented workflows: 6→1 capture, 5→1 comp intel, 10→1 scanners, delete 10 dead workflows.
3. ENHANCE | RSS feeds, PGVector, Telegram bot, email digests, doc auto-indexing, Deep Research agent.
4. GOVERN | Add HITL approval gates on SITREP/Red Team distribution. Formal bid/no-bid approval flow via Telegram.

## Consolidation Map
# | Cluster | Current Workflows | Count | Tab Affected | Problem | Target | Calls Before→After | UX Impact | Priority
1 | Capture Intel | capture-intel, capture-intel-modules, capture-hub, capture-plan, ooda-loop, pwin-calculator | 6 | Capture Plan | 3-4 separate webhooks. Each hits Postgres + Claude independently. 3-4x latency and API cost. | GDA.api.capture-mega | 4→1 | Page loads 60% faster. One spinner instead of four. | HIGH
2 | Comp Intel | competitor-watchlist, comp-intel 2, competitor-threat-score, competitor-field, incumbent-analysis | 5 | Comp Intel | 5 workflows query same competitor data. Each calls Claude separately. | GDA.api.compintel-mega | 3-5→1 | Cards render together. No partial load states. | HIGH
3 | Scanners | broad-opp-search, dept-opp-sweep, on-ramp-scanner, forecast-ingest, dpc-forecast-scraper, dhs-industry-day, golden-dome, amendment-monitor, change-detector, pre-sam-monitor | 10 | Background | 10 independent crons. No coordination. Silent failures. Most have no error handling. | GDA.cron.master-scanner | 10→1 | Reliability: one place to check "did overnight sweep complete?" | HIGH
4 | Opp Data | opp-tracker 2, opp-search, saved-opps, pipeline, launchpad-funnel, opp-classifier | 6 | Pipeline + Launchpad | Frontend calls different endpoints for same data filtered differently. | GDA.api.pipeline-mega | 2-3→1 | Consistent data. No stale cache mismatches between views. | HIGH
5 | Dashboard | dashboard-intel 2, dashboard-intel-deep, ops-dashboard-data, intel-feed, trends, chart-generator | 6 | Dashboard | 6 workflows power one dashboard. Panels load at different speeds. | GDA.api.dashboard-mega (keep SITREP separate) | 5-6→2 | KPIs load as one unit. Faster dashboard render. | MEDIUM
6 | Dead/Superseded | AI Decision Engine [SUPERSEDED], Market Learning [SUPERSEDED], ai-agent 2, general-chat, capture-execution-suite, challenge-ledger, exit-manager, opp-daily, broad-opp-pull, clear-stale-trade | 10 | None | Dead workflows with reachable unauthenticated webhooks. Audit noise. | DELETE all | — | 30+ fewer audit findings. Cleaner instance. | MEDIUM
7 | Documents | doc-ingest, batch.doc-ingest, doc-compare, rag-query | 4 | Doc Ingest | Two ingest versions (single + batch). RAG query separate. | Merge batch into doc-ingest with mode param | Minimal | Cleaner codebase. | LOW
8 | Relationships | relationship-tracker, relationships, contacts, teaming-finder, win-loss-db | 5 | Relationships | 5 CRUD workflows for related data. | GDA.api.relationships-mega | 3→1 | Tab loads faster. | LOW
9 | Financial | aop-tracker, aop-definitions, FY Revenue Calc, nightly-fy-revenue-calc | 4 | Financial Bible | Two revenue calcs (manual + nightly). | Merge aop-tracker + definitions. Keep nightly cron. | 2→1 | Financial tab loads as one unit. | LOW
10 | Dev Utils | grep-appjsx, read-appjsx, ssh-read-file, e2e-test, workflow-mega-test, frontend-e2e | 6 | None | Session-specific test workflows. Overlap. | Keep ssh-read-file. Delete session-specific tests. | — | Less clutter. | LOW

## Gap Analysis
# | Domain | What You Have | WHAT IS MISSING | Impact on You | Solution | Template / Pattern | Priority
1 | Intel Feeds | GovTribe, DPC, DHS/Golden Dome monitors | NO defense news RSS. No real-time SAM.gov. No automated news. | Find out about agency changes days late. Intel is reactive. | RSS Feed Trigger → Claude → email. Apify SAM.gov → webhook. | #5103, Apify SAM.gov | CRITICAL
2 | Semantic Search | RAG query but keyword-only. No vector embeddings. | Cannot search by concept. "Find C5ISR opps" doesnt work. | 420+ opps unsearchable by concept. Connections invisible. | PGVector on existing Postgres. Zero new infrastructure. | #10157 (Agentic RAG) | CRITICAL
3 | SAM.gov Streaming | Pre-SAM monitor INACTIVE. Batch/daily only. | No real-time new opportunity detection. | Competitors with real-time alerts get first-mover advantage. | Apify SAM.gov → webhook. Or SAM.gov API on 15-min cron. | Apify SAM.gov | CRITICAL
4 | Mobile Access | Desktop web only. | NO Telegram bot. No mobile alerts or approvals. | During travel/meetings — GDA is unreachable. | Telegram Bot: private, free, instant. Voice notes → actions. | Telegram patterns | HIGH
5 | Doc Auto-Index | Manual trigger ingest only. | New RFPs sit unindexed in folders. | Drop RFP, forget to ingest, cant query it later. | Google Drive Trigger → chunk → embed into PGVector. | #2753 (94,941 views) | HIGH
6 | Competitor Web | GovTribe data only. No live crawling. | Cannot monitor competitor press, hiring, capabilities. | Miss competitor moves and partnerships. Stale comp intel. | Firecrawl + AI Vision fallback for resilient scraping. | Firecrawl + Vision pattern | HIGH
7 | AI Chat Memory | chat-simple with no persistent memory. | Every chat starts from zero. No multi-tool agent. | Repeat setup every session. AI has amnesia. | AI Agent + Postgres Chat Memory + PGVector + SQL. | #10157, #3414 | HIGH
8 | Deep Research | Predictive intel is single-shot Claude. No multi-step. | Cannot do autonomous deep-dive research on a competitor or program. | Miss nuanced intel that requires following multiple leads. | Deep Research agent pattern: multi-step Perplexity → synthesize. | #2883 (21,345 views) | HIGH
9 | Live Web Research | Static Claude analysis. No real-time search. | Cannot query recent agency/program news during capture. | Capture intel based on stale data. | Perplexity node (core). Nightly per active opp. | Perplexity (core) | MEDIUM
10 | Calendar Sync | No calendar integration. | No auto-created events for due dates or review gates. | Manual deadline tracking. Risk of missed dates. | Google Calendar — auto-create from capture milestones. | Google Calendar (core) | MEDIUM
11 | Email Digests | Daily briefing INACTIVE. | No passive intel delivery. Must log in. | You check or you miss it. | Schedule → Postgres → Claude → HTML → Gmail. | #10776 | MEDIUM
12 | HITL Governance | Red Team and SITREP distribute without approval. | No approval gate before sensitive outputs go to stakeholders. | Risk of distributing AI-generated content without review. | Send-and-Wait on Telegram before distribution. | #2907 (16,049 views) HITL pattern | MEDIUM
13 | Gov Portal Nav | SAM.gov via API only. | Cannot navigate interactive JS-heavy portals. | Some data locked behind interactive portals. | Browserbase + AI Vision fallback. | Browserbase node | LOW
14 | Advanced Docs | No OCR. No scanned PDF handling. | Cannot process scanned RFPs. | Occasional scanned docs require manual work. | PDF Vector — OCR, markdown, AI extraction. | PDF Vector node | LOW

## Templates & Patterns
ID | Template Name | Views | What We Steal | GDA Adaptation | Source | URL
5103 | RSS Feed Analysis w/ AI Risk Scoring | 411 | Daily RSS + webpage → AI risk categorize → HTML email | Morning Briefing: defense RSS → Claude → SITREP email | n8n.io | https://n8n.io/workflows/5103
10157 | Agentic RAG & PGVector (Local Doc Q&A) | 541 | Multi-tool AI: vector + SQL + doc retrieval on Postgres | GDA RAG chatbot: search capture plans + SQL pipeline + SOW retrieval | n8n.io | https://n8n.io/workflows/10157
2883 | Open Deep Research — Autonomous Agent | 21345 | Autonomous multi-step research: search → read → follow leads → synthesize | Deep-dive competitor/program research. Multi-step Perplexity intelligence. | n8n.io | https://n8n.io/workflows/2883
2753 | RAG Chatbot w/ Google Drive & Auto-Embed | 94941 | Drive Trigger → auto-embed docs → vector store → chatbot | Auto-indexing: RFP dropped in Drive → embedded → queryable instantly | n8n.io | https://n8n.io/workflows/2753
2907 | Human-in-the-Loop Email Response | 16049 | AI generates → sends for human approval → distributes after OK | SITREP/Red Team approval: Claude generates → Telegram approve → distribute | n8n.io | https://n8n.io/workflows/2907
3414 | Slack AI Chatbot w/ RAG & Claude | 7366 | Drive → vector store → Claude Agent + memory → chat response | Telegram bot pattern: same architecture, Telegram output instead of Slack | n8n.io | https://n8n.io/workflows/3414
6935 | Contract Renewals & Reminders | 110 | Scheduled → AI notifications → Send-and-Wait approvals | Capture milestone alerting: deadline scan → Telegram with ack | n8n.io | https://n8n.io/workflows/6935
10776 | Daily News w/ AI & Email Reports | 312 | Multi-source RSS → classify → commentary → email | Morning briefing with strategic commentary layer | n8n.io | https://n8n.io/workflows/10776
8497 | Enterprise CLM w/ AI Risk |  | Intake → AI extraction → risk scoring → obligation tracking | Option year alerts, renewal tracking, recompete monitoring | n8n.io | https://n8n.io/workflows/8497
5974 | Pipeline Analytics w/ OpenAI & Sheets |  | CRM query → anomaly detection → alerts → archive | Detect stalled captures, declining PWin, bottleneck opps | n8n.io | https://n8n.io/workflows/5974
2786 | Branded AI Website Chatbot | 88237 | Chat Trigger → Agent → calendar → capture | Embedded chat on gda.csr-llc.tech for natural language Q&A | n8n.io | https://n8n.io/workflows/2786
Apify | SAM.gov Opportunities Monitor |  | Real-time SAM.gov → webhook on new/modified opps | New NAICS matches → webhook → auto-ingest to pipeline | Apify | https://apify.com/m_mamaev/sam-gov-opportunities-monitor

## Master Roadmap
# | Phase | Stream | Action | Closes | What It Does For You | Days | Priority | Status
PHASE 0 — HARDEN (This Week)
1 | P0 | Harden | Batch-add webhook auth (129 endpoints) | Security | Every webhook gets X-GDA-Key header. Closes biggest security hole. | 2 | CRITICAL | ✅ S-133
2 | P0 | Harden | Unified error handler → 74 workflows | Security | GDA.error.handler catches all failures → Postgres log → Telegram alert. | 3 | CRITICAL | ✅ S-133
3 | P0 | Harden | Parameterize top 35 SQL queries | Security | Eliminate SQL injection on most exposed queries. | 4 | HIGH | ✅ S-136→S-142 (22 WFs, 32 nodes)
4 | P0 | Harden | Configure Task Runners for heavy workflows | Stability | Isolate 51-node export, 36-node SITREP, RAG into separate containers. | 1 | HIGH | ✅ S-136
5 | P0 | Harden | Update n8n v2.9.2 → v2.14.2 | Security | 6 versions of security patches + performance improvements. | 1 | HIGH | ✅ S-133
6 | P0 | Harden | Delete dead workflows + unused creds | Cleanup | Remove 10 superseded workflows + 22 unused credentials. | 1 | MEDIUM | ✅ S-133
7 | P0 | Harden | Add HITL approval gates (SITREP/Red Team) | Governance | Send-and-Wait on Telegram before distributing AI outputs. | 2 | MEDIUM | ✅ S-137→S-138
8 | P0 | Harden | Configure 30-day execution data pruning | Security | Stop accumulating execution data indefinitely. | 0.5 | LOW | ✅ S-133
PHASE 1 — CONSOLIDATE + FIRST ENHANCEMENTS (Weeks 2-3)
9 | P1 | Consolidate | Merge 10 scanners → master-scanner | Reliability | One cron, one error handler, one completion log. | 3 | HIGH | ✅ S-133
10 | P1 | Consolidate | Merge 6 capture intel → capture-mega | UX Speed | Capture Plan tab: 4 API calls → 1. 60% faster page load. | 4 | HIGH | NOT NEEDED (already merged S-133)
11 | P1 | Consolidate | Merge 5 comp intel → compintel-mega | UX Speed | Comp Intel tab: 5 calls → 1. Cards render together. | 3 | HIGH | NOT NEEDED (already merged S-133)
12 | P1 | Consolidate | Merge 6 opp data → pipeline-mega | UX Speed | Pipeline/Launchpad: 3 calls → 1. Consistent data. | 3 | HIGH | ✅ S-138→S-140 (dashboard-mega)
13 | P1 | Enhance | Morning Intel Briefing (RSS+Claude+Email) | Gap 1,11 | Defense news → Claude classifies → email at 0600. | 3 | CRITICAL | ✅ S-133
14 | P1 | Enhance | SAM.gov Real-Time Scanner | Gap 3 | New NAICS matches in pipeline within 15 minutes. | 4 | CRITICAL | DEFERRED (no SAM API key)
PHASE 2 — FOUNDATION (Weeks 3-4)
15 | P2 | Consolidate | Merge dashboard workflows → dashboard-mega | UX Speed | Dashboard KPIs load as one unit. | 3 | MEDIUM | ✅ S-138 (dashboard-mega)
16 | P2 | Consolidate | Delete 10 dead/superseded workflows | Cleanup | Reduce audit noise by ~30 findings. | 0.5 | MEDIUM | ✅ S-136 (14 WFs deleted)
17 | P2 | Enhance | PGVector Semantic Search | Gap 2 | Search by concept across 420+ opps. On YOUR Postgres. | 5 | CRITICAL | ✅ S-136 (761 vectors, 13MB)
18 | P2 | Enhance | Agentic RAG Chatbot | Gap 2,7 | Multi-tool AI: vector + SQL + docs. Persistent memory. | 7 | HIGH | DEFERRED (Phase 3)
19 | P2 | Enhance | Telegram Bot | Gap 4 | Private bot. "Pipeline health" from phone. Approve bids. | 4 | HIGH | ✅ S-133+S-137 (Telegram bot)
PHASE 3 — EXPANSION (Month 2)
20 | P3 | Enhance | Competitor Crawler (Firecrawl + Vision) | Gap 6 | Weekly crawl of competitor sites. Vision fallback for resilience. | 5 | HIGH | NOT STARTED
21 | P3 | Enhance | Auto-Index Document Pipeline | Gap 5 | RFP in Drive → queryable in 60 seconds. KB grows automatically. | 5 | HIGH | NOT STARTED
22 | P3 | Enhance | Deep Research Agent | Gap 8 | Autonomous multi-step research on competitors/programs. | 4 | HIGH | NOT STARTED
23 | P3 | Enhance | Google Calendar Milestone Sync | Gap 10 | Due dates auto-appear in calendar. Mobile reminders. | 3 | MEDIUM | NOT STARTED
24 | P3 | Enhance | Embedded Chat Widget | Gap 7 | Chat bubble on platform. Ask questions without clicking tabs. | 3 | MEDIUM | NOT STARTED
PHASE 4 — POLISH (Month 2-3)
25 | P4 | Enhance | Perplexity Nightly Research | Gap 9 | Every night: active opps → Perplexity research → Daily Actions. | 4 | MEDIUM | NOT STARTED
26 | P4 | Enhance | Scheduled Email SITREP | Gap 11 | Weekly SITREP auto-emailed. Zero effort. | 3 | MEDIUM | NOT STARTED
27 | P4 | Enhance | Capture Milestone Alerts (Telegram) | Gap 10 | Deadlines within 7/14/30 days → Telegram alerts. | 3 | MEDIUM | NOT STARTED
28 | P4 | Enhance | SMS Critical Failsafe (Twilio) | — | Emergency SMS for critical deadlines. Last-resort. | 2 | MEDIUM | NOT STARTED
29 | P4 | Enhance | n8n Quick-Entry Form | — | Bookmarked URL: drop opp, upload RFP. Mobile-friendly. | 2 | MEDIUM | NOT STARTED
30 | P4 | Harden | Parameterize remaining 229 SQL queries | Security | Full SQL injection hardening. | 5 | MEDIUM | ✅ S-136→S-142 (merged with #3)
PHASE 5 — ADVANCED (Month 3)
31 | P5 | Enhance | Browserbase + Vision Gov Portal Agent | Gap 13 | AI navigates interactive portals. Vision fallback for layout changes. | 5 | LOW | NOT STARTED
32 | P5 | Enhance | PDF Vector Doc Processing | Gap 14 | OCR scanned RFPs. Handle image-heavy docs. | 3 | LOW | NOT STARTED
33 | P5 | Enhance | Autonomous Morning Orchestrator | All | Master loop at 0600: scan → classify → alert → report. | 3 | LOW | NOT STARTED
34 | P5 | Consolidate | Remaining merges (relations, financial, dev utils) | Cleanup | Final cleanup pass. | 4 | LOW | NOT STARTED

## Effort Summary
Phase | Timeframe | Harden Days | Consolidate Days | Enhance Days | Total Days | What You Get
Phase 0 | This week | 14.5 | 0 | 0 | 14.5 | All 129 webhooks secured. Error handling on 74 workflows. SQL injection fixed. n8n updated. Task Runners configured. HITL governance gates added.
Phase 1 | Weeks 2-3 | 0 | 13 | 7 | 20 | 4 mega-workflows consolidate 27 old ones. Morning briefing running. SAM.gov scanner live.
Phase 2 | Weeks 3-4 | 0 | 3.5 | 16 | 19.5 | Dashboard consolidated. PGVector semantic search. RAG chatbot. Telegram bot on your phone.
Phase 3 | Month 2 | 0 | 0 | 20 | 20 | Firecrawl competitor monitoring. Auto-indexing docs. Deep Research agent. Calendar sync. Embedded chat.
Phase 4 | Month 2-3 | 5 | 0 | 14 | 19 | Email SITREPs. Milestone alerts. SMS failsafe. Quick-entry form. Remaining SQL hardening.
Phase 5 | Month 3 | 0 | 4 | 11 | 15 | Browser automation. PDF OCR. Autonomous morning loop. Final cleanup.
TOTAL | ~3 months | 19.5 | 20.5 | 68 | 108 | From 148 fragmented workflows → ~100 clean, secure, consolidated workflows. Mobile access. Semantic search. Proactive intelligence. Governed outputs.
COMPLETED (S-136→S-144) | Apr 7, 2026 |  |  |  |  | P0 Harden DONE: SQL param 22WF/32 nodes, Task Runners, HITL gates, dead WF cleanup. P2: Dashboard mega (5→3 API calls), PGVector 761 vectors, Contract Waterfall API. Cron fleet stabilized (~400 errors/day→0). Collation fixed.

## Operator Interface
Channel | When You Use It | What You Can Do | Why This One | Phase
gda.csr-llc.tech (EXISTS) | At desk, deep work | Full platform: all tabs, all AI tools, all charts. This is HQ. | Primary interface. Everything else supplements. | —
Telegram Bot (ADD) | On the move, quick checks, approvals | Text "pipeline health" "CRITICAL deadlines" "run briefing". Voice notes → actions. Approve/reject bids with a tap via Send-and-Wait. | Replaces Slack/Teams/WhatsApp. Free. Private. Works everywhere. Richest messaging API. Also serves as HITL approval channel. | P2
Email Digest (ADD) | Morning with coffee | Morning briefing: new SAM opps, defense news, pipeline changes, deadlines. Weekly SITREP auto-delivered. | Passive intel. Inbox you already check. Zero new apps. | P1+P4
Embedded Chat (ADD) | Already on platform | Natural language Q&A: "What did we submit for IEW&S?" RAG-powered answers from your own data. | For when youre at the computer and want conversational access. | P3
SMS Twilio (ADD) | Emergency only | Receives: "IEW&S due in 24hrs — 2 open items." Thats it. | Last-resort failsafe. Reaches you if you ignore everything else. Pennies/month. | P4
n8n Form (ADD) | Quick mobile data entry | Bookmarked URL → drop opp URL, upload RFP, request capture plan. | Faster than full platform nav for simple submissions. | P4
Slack/Teams/WhatsApp | KILLED | — | Nobody on the other end. Solo operator doesnt need team collab tools. | —

## Current Capabilities
# | Domain | Capability | Workflow | Active | Auth? | Err Handler?
1 | Opp Intel | Opportunity Tracker (420+) | opp-tracker 2 | Y | Y | Y
2 | Opp Intel | Opportunity Search | opp-search | Y | Y | Y
3 | Opp Intel | Saved Opportunities | saved-opps | Y | Y | Y
4 | Opp Intel | GovTribe Feed | govwin-feed | Y | Y | Y
5 | Opp Intel | Broad Opp Search | broad-opp-search | Y | Y | Y
6 | Opp Intel | On-Ramp Scanner | on-ramp-scanner | Y | Y | Y
7 | Opp Intel | Dept Sweep | dept-opp-sweep | Y | Y | Y
8 | Opp Intel | Forecast Ingest | forecast-ingest | Y | Y | Y
9 | Opp Intel | Amendment Monitor | amendment-monitor | Y | Y | Y
10 | Opp Intel | Change Detector | change-detector | Y | Y | Y
11 | Capture | Capture Plan (Shipley v2) | capture-plan | Y | Y | Y
12 | Capture | Auto Capture Plans | auto-capture-plans | Y | Y | Y
13 | Capture | Capture Intelligence | capture-intel | Y | Y | Y
14 | Capture | OODA Loop | ooda-loop 2 | Y | Y | Y
15 | Capture | PWin Calculator | pwin-calculator | Y | Y | Y
16 | Capture | Opp Classifier | opp-classifier | Y | Y | Y
17 | Capture | Stage Promotion | opp-stage-promote | Y | Y | Y
18 | Comp Intel | Competitor Watchlist | competitor-watchlist | Y | Y | Y
19 | Comp Intel | Comp Intel Dashboard | comp-intel 2 | Y | Y | Y
20 | Comp Intel | Threat Score | competitor-threat-score | Y | Y | Y
21 | Comp Intel | Weekly Scan | weekly-comp-scan | Y | Y | Y
22 | Comp Intel | Incumbent Analysis | incumbent-analysis | Y | Y | Y
23 | Proposal | Doc Ingest | doc-ingest | Y | Y | Y
24 | Proposal | Doc Compare | doc-compare | Y | Y | Y
25 | Proposal | RAG Query | rag-query | Y | Y | Y
26 | Proposal | Red Team | red-team | Y | Y | Y
27 | Proposal | Black Hat | black-hat | Y | Y | Y
28 | Proposal | Compliance Matrix | compliance-matrix | Y | Y | Y
29 | Proposal | Clause Library | clause-library | Y | Y | Y
30 | Proposal | Export Engine (51 nodes) | export-engine | Y | Y | Y
31 | Financial | AOP Tracker | aop-tracker | Y | Y | Y
32 | Financial | IDIQ Tracker | idiq-tracker | Y | Y | Y
33 | Financial | FY Revenue Calc | FY Revenue Auto-Calc | Y | Y | Y
34 | AI | Priority Score v2.1 | Priority Score v2.1 | Y | Y | Y
35 | AI | Predictive Intel | predictive-intel | Y | Y | Y
36 | AI | Smart Recommender | Smart Recommender | Y | Y | Y
37 | AI | Pattern Extractor | Pattern Extractor | Y | Y | Y
38 | AI | Daily Actions | daily-actions | Y | Y | Y
39 | AI | Wargame Simulator | wargame | Y | Y | Y
40 | Reporting | SITREP (36 nodes) | sitrep 2 | Y | Y | Y
41 | Reporting | Dashboard Intel | dashboard-intel 2 | Y | Y | Y
42 | Reporting | Chart Generator | chart-generator | Y | Y | Y
43 | Reporting | Intel Feed | intel-feed | Y | Y | Y
44 | Collab | Email Drafter | email-drafter | Y | Y | Y
45 | Collab | Meeting Notes | meeting-notes 2 | Y | Y | Y
46 | Relations | Relationship Tracker | relationship-tracker | Y | Y | Y
47 | Relations | Teaming Finder | teaming-finder | Y | Y | Y
48 | Relations | Win/Loss DB | win-loss-db | Y | Y | Y
49 | Platform | Deploy Pipeline | deploy | Y | Y | Y
50 | Platform | Health Scan | health-scan | Y | Y | Y
51 | Platform | E2E Tests (32/32) | e2e-test suites | Y | Y | Y
52 | Platform | Data Sync v2 | DataSync_v2 | Y | Y | Y
53 | Platform | System Watchdog | System Watchdog | Y | Y | Y
54 | Platform | Chat Simple | chat-simple | Y | Y | Y
55 | Platform | Knowledge Base | knowledge-base | Y | Y | Y
56 | Risk | Risk Intel | risk-intel | Y | Y | Y
57 | Risk | Auto Risk Gen | auto-risk-generation | Y | Y | Y
58 | Risk | Challenge/Exit Monitor | challenge-exit-monitor | Y | Y | Y
59 | Strategic | NDAA/FAR Ingest | ndaa-far-ingest | Y | Y | Y
60 | Strategic | FPDS Enrichment | fpds-enrichment | Y | Y | Y
61 | Notifications | Telegram One-Way Alerts | GDA.notify.telegram | Y | Y | Y
62 | Notifications | Telegram Two-Way Chat | GDA.bot.telegram-chat | Y | Y | Y
63 | Platform Ops | Error Log API | GDA.api.error-log | Y | Y | Y
64 | Platform Ops | Error Log Frontend Viewer | PlatformHealthPage.jsx | Y | N/A | N/A
65 | Platform Ops | MCP Proxy Write Action | GDA.mcp.proxy | Y | Y | N/A