## S-155 Updates
GDA COMMAND PLATFORM ASSESSMENT — S-155 UPDATES
Date: April 10, 2026 (late afternoon)
Sessions covered: S-155
CATEGORY | S-154 STATE | S-155 STATE
Active workflow count | 151 (memory) | ✅ 152 (verified via n8n_audit_instance)
n8n version | 2.47.1 (memory — WRONG) | ✅ 2.14.2 (actual, 1 behind at 2.15.1)
Total audit findings | Not measured | 934 (0 Crit / 1 High / 77 Med / 856 Low)
Unauthenticated webhooks | 0 claimed | 1 HIGH found (capture-plan-cards) — NOW FIXED
Unused credentials | Not measured | 6 unused — prune-before-rotate candidates
SQL nodes unparameterized | 247 (memory) | 249 (audit confirmed, +31 expression-in-Query subset)
FIXES DELIVERED
capture-plan-cards Auth Guard | ⚠️ Origin-trust backdoor (fake Origin header bypasses auth) | ✅ FIXED — dual-key only (gda-api OR gda-deploy). Smoke-tested 3 scenarios.
gist-update Format Gist | ⚠️ Read body.broken only — broken_blocked dropped | ✅ FIXED — accepts broken_blocked (preferred) OR broken (legacy), handles string/array/object/null
Auth Code node sweep | ⏸️ Carried from S-153 (2 fixed, sweep incomplete) | ✅ VERIFIED CLEAN — 1 SQL match was intentional 2-key defense-in-depth on GDA.dev.deploy, not a bug
IN-FLIGHT (PARTIAL)
Switch/If sweep (typeVersion 3+ missing options) | 1 known (action-history Route, fixed S-154) | 🟡 20 of 22 victims identified via postgres sweep. PATCH NOT YET APPLIED. Carried to S-156 #2.
NEW FINDINGS THIS SESSION
Origin-trust backdoor pattern | Not known | ⚠️ NEW — Code nodes with `origin.includes(trusted)` bypass auth on forged Origin header. Fixed in 1 workflow, platform-wide sweep needed.
capture-plan-cards error 200 response | Not known | ⚠️ NEW — Throws Unauthorized in Code node but returns bare 200 empty body because Respond node is on parallel happy-path. Needs error→401 path.
GDA.dev.deploy 2-key defense-in-depth | Undocumented | ✅ DOCUMENTED — Layer 1 x-gda-key at webhook node + Layer 2 x-gda-auth/deploy_key at Code node. By design, not a bug.
BLOCKERS
Chrome connector javascript_tool | ✅ Working | ⚠️ DIED MID-SESSION — 2 consecutive 4-min timeouts. All SSH-dependent work blocked (KPI #5, column sweep #7, intel log #10).
Encryption key rotation | ⏸️ Deferred | ⏸️ Still deferred — runbook started, 13 creds inventoried, recommend bundling with n8n 2.14.2 → 2.15.1 upgrade
VERIFIED PLATFORM NUMBERS (unchanged S-154 → S-155)
Active opportunities | 173 | 173 (no change)
Pipeline value | $2.303B | $2.303B (no change)
PURSUE count | 103 | 103 (no change)
Capture plans | 38 | 38 (no change)
Competitors in watchlist | 35 | 35 (no change)
Active risks | 229 | 229 (no change)
Active workflows | 151 (memory) | 152 (audit corrected)
── S-155 CONTINUATION (turn 2) ──
Version pinning (Item #8) | Partial: 3 of 5 pinned | ✅ COMPLETE — 5 of 5 critical workflows pinned. opp-tracker 2 added v1 (versionId 3071)
Version history platform gap | Unknown | 🟠 NEW — 4 of 5 "critical" workflows had ZERO history pre-session. UI/full-update edits don't create version entries. Systemic.
RR-25 duplicate " 2" workflows | Delete candidates | ⚠️ CORRECTED — opp-tracker 2 + ooda-loop 2 are LIVE canonicals, not dupes. Rename don't delete.
Item #4 launchpad side | Assumed needs wiring | ✅ ALREADY WIRED — summary.totalAlloc sums plan_data->>'allocated_revenue' already. No change needed.
Item #4 aop-tracker side | Assumed needs wiring | ⏸️ DESIGN BLOCKER — capture plans lack fiscal_year field; aop-tracker has hardcoded staleness. Deferred.
Item #10 intelligence log | "Broken since S-148" | 🎯 ROOT CAUSE — OODA writes non-existent cols (workflow_name, session_id, target, summary, generated_at) + SQL injection. 22 silent fails/week. intel-feed never triggered.
OODA execution rate | Unknown | 22 successful runs/week (not dormant). Every run silently fails the intel-log write.
gda_intelligence_log canonical schema | Memory said logged_at | CORRECTED: (id integer, timestamp timestamptz, source text, agency text, finding text, category text, priority text, created_at timestamptz)
Item #6 daily-actions bottleneck | Unknown | ~93% Claude API latency. ~600ms postgres. Parallelize buys nothing. Cache on (date, opps_hash) buys 14s on hit.
Item #6 ooda-loop bottleneck | Unknown | ~62% Claude, ~28% Tavily. Parallelize pre-Claude work saves 8s (29→21s). Cache Tavily stacks on top.
#6 recommendation | Unknown | Option B (parallelize ooda) + narrow Option C (cache daily-actions). Defer Option A (async).
── S-155 CONTINUATION (turn 3) ──
Switch/If sweep methodology | Turn 1: 22 victims identified | 🚨 CORRECTED — query checked wrong JSON path. Mix of false positives and real victims. Must re-sweep at per-rule-condition level (parameters.rules.values[*].conditions.options).
capture-plan Route Action | Listed as victim #5 | ✅ ALREADY FIXED (likely S-153) — caseSensitive+typeValidation set at rule-condition level. False positive in turn 1 sweep.
action-history Route | Fixed S-154 | ✅ STILL FIXED — re-verified this turn. Per-rule-condition level has caseSensitive:true + typeValidation:loose + version:2. False positive in turn 1 sweep.
trends Route Action | Listed as victim | 🔴 GENUINE VICTIM — rules.values[*].conditions has NO options key at all. Pattern confirmed as real bug. Fix template: add caseSensitive:true + typeValidation:loose + version:2 to each rule condition.
Switch/If real victim count | 22 assumed | UNKNOWN until re-sweep with corrected query. Could be anywhere from 2 to 20.
Chrome connector reliability | 1 failure (turn 2) | 🟠 2 failures in 3 turns. 4-minute timeout pattern. Recovery only at chat-turn boundary.
── S-155 CLOSE (turn 4) ──
RR-37 Format Gist array handling | Discovered turn 4 | ✅ SHIPPED same session — Fix #3 applied normalize-any-shape pattern from Fix #2 to completed and next_steps fields. Workflow updatedAt 19:58:08 UTC.
Fix #3 verification status | Deploy confirmed via MCP | ⚠️ DEPLOYED BUT SMOKE TEST INCOMPLETE — Chrome died on the post-patch test fetch. Workflow live, no new errors in execution history post-patch. S-156 turn 1 first-action: re-verify via test gist push.
Gist workflow execution retention | Unknown | 📊 Discovered: successes are NOT retained in execution_entity, only errors. Post-deploy verification of gist-update MUST use gist content read (gist.githubusercontent.com/.../raw), not execution history.
R-SR-09 memory update | Not in memory | ✅ Memory #30 added with 4-artifact protocol. Memory #20 (closed backlog state) removed to make room.
RR-36 Chrome connector reliability | Medium severity | 🚨 PROMOTED to HIGH severity — 3 failures in 4 S-155 turns (~75% failure rate). Systemic, not intermittent. Dominant reliability blocker.
Fixes shipped in S-155 (final) | 2 | 3 — added RR-37 Fix #3 as same-session follow-through on Fix #2.
Debt items closed in same session | 3 | 4 — Fix #3 (RR-37 array handling) closes the follow-through that Fix #2 started.

## S-154 Updates
GDA COMMAND PLATFORM ASSESSMENT — S-154 UPDATES
Date: April 10, 2026 (afternoon)
Sessions covered: S-154
CATEGORY | S-153 STATE | S-154 STATE
Platform Health (real endpoints) | 17/19 (89%) baseline | ✅ 19/19 (100%) post-S154 fixes
S-153 "58% health" number | ❌ FABRICATED | ✅ SUPERSEDED — based on invented endpoint names
Endpoint Validation Method | Workflow names (WRONG) | ✅ grep of App.jsx api.post() calls (correct)
Real frontend endpoint count | Claimed 24 (14 fabricated) | ✅ 19 (verified via grep)
gda-action-history | 🔴 Empty 200 (silent fail) | ✅ FIXED — save + list + tab:all all working
gda-predictive-intel | 🔴 Empty 200 (SQL crash) | ✅ FIXED — has_capture_plan subquery
cron.pipeline-health-digest | 🔴 Silently failing every tick | ✅ FIXED — 5 layered bugs resolved
capture-plan Enrich nodes | ⚠️ Silently failing enrichment | ✅ FIXED — 3 nodes patched
cron.stage-auto-promote SQL injection | ⚠️ Inline interpolation | ✅ HARDENED — $1 parameterized
Legacy queryParams pattern sweep | 🔴 Projected 50+ nodes | ✅ CLOSED — only 6 across 4 workflows
NEW FINDINGS THIS SESSION
Bug class: non-existent columns in SQL | NEW | Fix-once-ignore-pattern. Found has_capture_plan, scored_at, created_at, cabinet_department referenced in multiple workflows. R-DB-05 documents canonical schema.
Bug class: typeVersion 3+ Switch missing options | NEW | Found in action-history Route node. Causes output 0 to fire regardless of match. R-WR-16 documents required pattern.
Bug class: wrong table names | NEW | gda_risk_register vs risk_register. Only non-gda-prefixed production table. R-DB-06 documents.
S-153 methodology failure | POSTMORTEM | Fabricated endpoint list from workflow names. 14 of 24 endpoints tested were invented. R-WR-15 requires grep of App.jsx as source of truth.
VERIFIED PLATFORM NUMBERS (post-S154)
Active opportunities | 173 | stage NOT IN (No-Bid, Cancelled, No-Go)
Pipeline value | $2.303B | SUM(estimated_value) on active opps — matches S-145
PURSUE count | 103 | In Qualified stage per funnel
Capture plans | 38 | 15 linked to opp_tracker via opp_id
Competitors in watchlist | 35 | status=active
Active contracts | 5 | gda_active_contracts
Active risks | 229 | risk_register, case-insensitive active/open status
New opps in last 24h | 27 | By synced_at
Opps scored in last 24h | 751 | By updated_at where ai_analysis NOT NULL

## S-147 → S-153 Updates
GDA COMMAND PLATFORM ASSESSMENT — S-147 → S-153 UPDATES
Date: April 10, 2026 10:24 AM ET
Sessions covered: S-147, S-148, S-149, S-150, S-151, S-152, S-153
CATEGORY | S-146 STATE | S-153 STATE
Active Workflows | 151 | 152 (+1 GDA.api.capture-plan refactored)
Total Workflows | 155 | 155 (stable)
Opportunities | 729 | 729 (stable)
Capture Plans | 38 + auto-gen cron | 38 (15 linked to opp_tracker)
Funnel Qualified | 130 | 132 (cron-1 stage-auto-promote fix)
App.jsx | 5,220 lines | 5,236 lines (+16 — alloc field + helpers)
Active Bundle | index-(prior).js | index-_lFGxpmr.js
Phase 0 Hardening | 100% COMPLETE | ✅ HOLDING (no regressions S-147..S-153)
Money Formatter Consistency | Mixed (7 formatters) | ✅ UNIFIED via window.GDA_USD
Capture Plan Save | 🔴 SILENTLY ERRORING (postgres v2.5) | ✅ FIXED + verified end-to-end
Capture Plan Auto-Promote Cron | 🔴 BROKEN (missing column) | ✅ FIXED (updated_at column added)
Auto Capture Plan Cron | 🔴 BROKEN (queryParams key) | ✅ FIXED (queryReplacement)
Weekly Comp Scan Cron | 🔴 BROKEN (queryParams key) | ✅ FIXED (queryReplacement)
Frontend nginx Auth Header | 🔴 BROKEN (X-GDA-Auth) | ✅ FIXED (X-GDA-Key)
Gist Update Workflow Auth | 🔴 SILENTLY FAILING since Apr 9 | ✅ FIXED (accepts x-gda-key + x-gda-auth)
SEWP VI Plan Garbage Data | 🔴 $60B ghost | ✅ FIXED ($9.17M correct)
gda_allocation_m field | ✅ DEPLOYED | Total contract value share. Sacred (manual only, PROTECTED in jsonb_fill_blanks). Wired to capture plan card row 2 col 3.
Empty-field highlighting | ✅ DEPLOYED | Yellow #FEF3C7 + orange border #F59E0B on empty input fields. CpField function patched, all 3 render paths covered.
Pattern: postgres v2.5 queryParameters bug | OPEN — needs sweep | Multiple workflows use legacy queryParameters key which postgres v2.5 silently ignores. Need full sweep across all 152 active workflows. Found 3 in S-152.
Pattern: Auth Check Code node x-gda-auth only | OPEN — needs sweep | Code-node Auth Guards on multiple workflows check only headers[x-gda-auth], reject valid x-gda-key. Found 2 (capture-plan + gist-update). Likely more.
Pattern: typeVersion 2 If/Switch missing options.caseSensitive | OPEN — already documented | WORKFLOW RULES sheet of Build v61 documents this as known bug. Every new workflow keeps hitting it. Need defensive default in n8n_update_partial_workflow path.
Wire gda_allocation_m to AOP rollup | OPEN | Workflow P8AfP8P84xi33auD GDA.api.aop-tracker
Wire gda_allocation_m to Launchpad KPI | OPEN | Workflow vaRzM1Jl6HcXjuxs GDA.api.launchpad-funnel
Enrich 21 unlinked capture plans | OPEN | Most are RS3 task orders not in GovTribe. Need RS3 portal access.
Top-strip KPIs hardcoded | OPEN | ORDERS/SALES/EBIT/ROS/FUNDED BACKLOG/BACKLOG at lines 5184-5192 are placeholder strings. Need to wire to real data.
Senior DevOps Hardening Charter | IN-FLIGHT (this session) | Phase 1 consolidation, Phase 2 rules extraction, Phase 3 hardening with config locks, Phase 4 end-to-end validation.

## S-146 Updates
GDA COMMAND PLATFORM ASSESSMENT — S-145 UPDATES
Date: April 8, 2026
CATEGORY | S-144 STATE | S-145 STATE
Active Workflows | 134 | 151 (+17)
Active Opps | 674 (all in DoW) | 165 active / 387 total (15 depts)
Pipeline Value | $3.5B (inflated with junk) | $2.3B (clean GDA-relevant)
Departments | 1 (Department of War only) | 15 cabinet + Independent Agencies
PURSUE Count | 1 | 24
Capture Plans | 38 | 38 + auto-generation cron
Competitors w/ Landscapes | 35 / 0 | 35 / 35 (5 landscapes)
Contracts API | Returns 50 opps from wrong table | 5 real contracts from gda_active_contracts
DB Triggers | 1 | 3
Cron Jobs | ~20 | 29
E2E | 31/32 | 31/32
Git | 14a779d | 4fbd758
KEY RISKS RESOLVED
All opps classified as Department of War | RESOLVED | normalize_opp_hierarchy() trigger updated
315 non-GDA opps polluting pipeline | RESOLVED | No-Bid + NAICS gate trigger
Auth blocking all frontend calls | RESOLVED | 88 WFs + 59 Auth Guards patched
PURSUE opps stuck in No-Go | RESOLVED | Stage alignment — 39 rescued
Opp title click opens external link | RESOLVED | Title now expands detail panel
CC deploy white-screened site | RESOLVED | Rebuilt from git commit
REMAINING RISKS
P2 Financials shows opps as contracts | OPEN | CC needs to wire to contracts API
Comp Intel no landscape tabs | OPEN | Backend ready, CC frontend needed
Email Drafter E2E 404 | LOW | Path mismatch in health check, API works
Auto-analysis over-scoring | MITIGATED | Prompt overhauled, 14 re-scored
S-146 UPDATES (April 9, 2026)
Webhook Auth | 143/143 (100%) — was 129/129 at S-145. All 3 skipped WFs fixed. auto.e2e-test conflict resolved. | ✅ COMPLETE
Error Handler | 74/74 workflows attached — was 74/74. New handler ID: 2Swf6LP9AzFjHFYU (replaces BVOAC22J7MM2tsBg). | ✅ COMPLETE
Credential Cleanup | 13 credentials (was 12 at S-145 end, +1 Perplexity added). Schwab deleted. | ✅ CLEAN
SQL Injection Audit | Top workflow (capture-plan, 7 PG nodes) fully audited — parameterized. 58 WFs assessed. | ✅ AUDITED
Error Log Table | gda_error_log: 23 entries captured. Handler active and routing to Telegram. | ✅ OPERATIONAL
Active Workflows | 151 (was 151 at S-145) | STABLE
Total Workflows | 155 (was 155 at S-145) | STABLE
Opportunities | 729 (was 387 post-cleanup at S-145) | GROWTH
App.jsx | 5,220 lines (was 5,222 at S-145) | STABLE
Phase 0 Status | HARDENING 100% COMPLETE. All 5 carry items from S-133 resolved. | ✅ DONE

## Hardening Plan
# | Category | Finding | Count | Severity | Action | Technical How-To | Auto-Fix? | Days
1 | Webhooks | Unauthenticated webhooks on ACTIVE workflows | 129 | HIGH (SECURITY) | Add X-GDA-Key header auth to every webhook. One shared secret across all. | n8n_manage_credentials(create httpHeaderAuth) → n8n_update_partial_workflow batch. Script runs in ~2hrs. | YES | ✅ S-133→S-146 (143/143)
2 | Error Handling | Workflows with zero error handling | 74 | HIGH | Create GDA.error.handler: Error Trigger → log to Postgres → Telegram alert. Attach to all 74. | One handler workflow. Then set errorWorkflow on each via n8n_update_partial_workflow. Telegram notifies you of any failure. | PARTIAL | ✅ S-133→S-146 (74/74)
3 | SQL Injection | Postgres queries with expressions in Query field | 35 | HIGH (SECURITY) | Rewrite to use $1 parameterized queries. Move expression values to Query Parameters array. | Change "WHERE id = {{$json.id}}" to "WHERE id = $1" with params [$json.id]. Requires manual review per query. | YES | ✅ S-136→S-142
4 | Task Runners | Heavy workflows (51-node export, 36-node SITREP, RAG) can timeout the main process | — | HIGH | Configure n8n Task Runners to isolate heavy execution in separate Docker containers. | Add N8N_RUNNERS_ENABLED=true to .env. Configure runner container in docker-compose.yml. Prevents main n8n from blocking. | YES | ✅ S-136
5 | SQL Queries | Postgres queries without Query Parameters field at all | 229 | MEDIUM | Audit each. If static SQL — mark safe. If interpolates user input — parameterize. | Priority: the 35 with expressions first (item 3). Remaining 229 are lower risk but should be reviewed over time. | NO | 5
6 | Credentials | Hardcoded emails/phone numbers in workflow JSON | 9 | MEDIUM | Move to $env variables or n8n credential store. | Replace with $env.ALERT_EMAIL, $env.ALERT_PHONE. Add to ~/n8n-envision/.env. Restart Docker. | NO | 1
7 | Credentials | Unused credentials stored in n8n | 22 | MEDIUM | Delete all unused credentials. | n8n_manage_credentials(list) → identify unused → delete each. | YES | ✅ S-137
8 | Instance | n8n 6 versions behind (v2.9.2 → v2.14.2) | 1 | MEDIUM | Update n8n Docker image. | Update image tag in docker-compose.yml → docker compose down → up -d. Run full E2E test after. | NO | 1
9 | Data Retention | Excessive execution data stored indefinitely | 89 | LOW | Configure global 30-day pruning. | n8n Settings → Executions → pruneDataMaxAge=720 hours. | NO | 0.5
10 | Dead Code | Duplicate Stage Audit Logger + 10 superseded/inactive workflows | 12 | LOW | Delete duplicates and superseded workflows. | n8n_delete_workflow for each. Removes ~30 audit findings. | YES | ✅ S-136
11 | HITL Governance | Red Team, SITREP, and bid decisions distribute without human approval | — | MEDIUM | Add Send-and-Wait approval step before distributing Red Team/SITREP outputs. | On SITREP workflow: after Claude generates report → Telegram Send-and-Wait → you approve/edit → then email/distribute. | YES | ✅ S-137–S-138
12 | Notifications | Telegram bot deployed — E2E, errors, deploy alerts + two-way chat | 3 | LOW | RESOLVED S-135
S-153 ADDITIONS
13 | Workflow Bugs | postgres v2.5 queryParameters key (legacy, silently ignored) | 3+ found, full sweep needed | HIGH (DATA LOSS) | Sweep all postgres nodes; replace queryParameters with queryReplacement | n8n_update_partial_workflow patchNodeField for each affected node | YES | IN-FLIGHT S-153
14 | Workflow Bugs | Auth Check Code node only checks legacy x-gda-auth header | 2+ found, full sweep needed | HIGH (LOCKOUT) | Patch all Auth Check jsCode to accept x-gda-key, x-gda-auth, body fallback | n8n_update_partial_workflow patchNodeField with unified Auth Check pattern | YES | IN-FLIGHT S-153
15 | UI Consistency | 7 different money formatters across App.jsx producing inconsistent display | 7 formatters found | MEDIUM (UX) | Unify all formatters to delegate to canonical formatDollar = window.GDA_USD | sed-based App.jsx patching via gda-deploy webhook | YES | ✅ S-153 (DEPLOYED bundle index-_lFGxpmr.js)
16 | Data Integrity | Capture plan save silently failing since postgres v2.5 upgrade | 1 critical workflow | CRITICAL (DATA LOSS) | Fix If node options.caseSensitive + Postgres queryReplacement keys | n8n_update_partial_workflow on QgperN6cuOpfnb09 | YES | ✅ S-153 (FIXED + verified end-to-end)
--- S-154 ADDITIONS ---
RR-13 | Runtime | High | Legacy postgres queryParams key cleanup | Postgres node v2.5+ ignores options.queryParams silently; correct key is options.queryReplacement. Sweep of all active workflows. | Claude | ✅ DONE S-154 | S-152 / S-153 / S-154 | 6 nodes across 4 workflows fixed. Pattern sweep CLOSED. Much smaller scope than projected.
RR-14 | Runtime | High | Recurring empty-200 regression fix | Multiple endpoints returning HTTP 200 with empty body due to SQL crashes upstream of Respond node. | Claude | ✅ DONE S-154 | S-154 | Root caused to queryParams bug + non-existent columns + Switch misrouting. All instances fixed.
RR-15 | Runtime | Medium | Non-existent column references in SQL | Workflows written against schemas that never existed (has_capture_plan, scored_at, created_at, cabinet_department). | Claude | ✅ PARTIAL S-154 | S-154 | 4 fixed in predictive-intel + pipeline-health-digest + capture-plan enrich. Full instance sweep deferred to S-155.
RR-16 | Runtime | Low | typeVersion 3+ Switch missing caseSensitive options | Switch nodes at typeVersion 3+ require options.caseSensitive and typeValidation on every rule condition. | Claude | ✅ PARTIAL S-154 | S-154 | 1 fixed in action-history Route. Full sweep deferred.
RR-17 | Process | High | Endpoint validation methodology correction | S-153 report fabricated 14 of 24 endpoint names from workflow names. Correction: grep App.jsx for real api.post() calls. | Claude | ✅ DONE S-154 | S-154 | R-WR-15 rule added. S-153 validation table superseded.
--- S-155 ADDITIONS ---
RR-18 | Security | High | Origin-trust backdoor in Inner Auth Guard pattern | Code nodes used const origin = headers.origin; if trusted.some(o => origin.includes(o)) bypass auth. Origin header is client-controllable — any curl with forged Origin header bypassed entire auth check. Fixed in capture-plan-cards; platform-wide sweep needed for other Inner Auth Guard workflows. | Claude | 🟡 PARTIAL S-155 | S-155 | 1 of N fixed (capture-plan-cards 4szS4FHP1pW1PiG8). Sweep query for remaining: Code nodes with "origin.includes" in jsCode. Carried to S-156.
RR-19 | Data Integrity | High | gist-update Format Gist drops broken_blocked field | Format Gist Code node read only body.broken; recent payloads send body.broken_blocked; gist always rendered "Broken/Blocked: None" regardless of real debt. Defeated gist-update reporting flow. | Claude | ✅ DONE S-155 | S-155 | Fixed djgOV2vX3PIv9cvm. Accepts broken_blocked (preferred) OR broken (legacy). Handles string/array/object/null/empty.
RR-20 | Process | Medium | Auth Code node sweep verified clean | S-155 kickoff assumed ~30 victims remaining after S-153 partial fix. Postgres sweep across 151 active workflows returned only 1 match (GDA.dev.deploy) which was intentional 2-key defense-in-depth. S-153 fix has fully propagated. | Claude | ✅ DONE S-155 | S-155 | Sweep query closed. No remaining debt from x-gda-auth migration.
RR-21 | Runtime | Medium | Switch/If typeVersion 3+ missing caseSensitive options | 22 Switch/If nodes on typeVersion >= 3 missing options.caseSensitive and/or options.typeValidation. Causes routes to misfire (wrong case match) — same root cause as S-153 capture-plan bug and S-154 action-history bug. | Claude | 🟡 PARTIAL S-155 | S-155 | 20 of 22 victims identified. 2 middle-of-list truncated by webhook stdout cap. Patch deferred to S-156. Fix: add options.caseSensitive=true and options.typeValidation="strict".
RR-22 | Security | Medium | capture-plan-cards 200 on auth error | Workflow throws Unauthorized but returns bare 200 empty body because Respond node is on parallel happy-path branch. Caller gets no error signal. Same class as other Inner Auth Guard workflows. | Claude | ⏸️ S-156 | S-155 (found) | Add error→401 path. Also fix zero-row Respond bug (if Get Plans empty, Respond never fires).
RR-23 | Security | High | n8n 2.14.2 → 2.15.1 upgrade | Instance is 1 version behind. Memory previously said 2.47.1 (WRONG, corrected via audit). | Claude | ⏸️ DEFERRED | S-155 (found) | Bundle with encryption key rotation maintenance window. Both require restart.
RR-24 | Security | Medium | 6 unused credentials (prune candidates) | Audit flagged 6 credentials not used in any workflow or not used in past 90 days. Keeping them expands rotation re-entry surface and attack surface. | Claude | ⏸️ DEFERRED | S-155 (found) | Prune before encryption key rotation to reduce re-entry from 13 to 7. Can use n8n_manage_credentials delete.
RR-25 | Cleanup | Low | Duplicate " 2" workflow cleanup | GDA.api.action-items 2, GDA.api.sitrep 2, GDA.api.target-agencies 2 — orphaned copies surfaced by audit. | Claude | ⏸️ S-156+ | S-155 (found) | Delete candidates.
RR-26 | Security | Low | 4 PII/hardcoded-email findings | GDA System Watchdog phone in Send Alert SMS. GDA.api.action-items 2 emails in Generate ICS + Generate Digest. GDA.api.govwin-feed email in GovWin Get Token. GDA.api.sitrep 2 email in Send an Email. | Claude | ⏸️ S-156+ | S-155 (found) | Move to $env variables or n8n credential store.
--- S-155 CONTINUATION ADDITIONS ---
RR-27 | Security | High | OODA intelligence log writer uses non-existent columns + SQL injection | GDA.api.ooda-loop 2 (pkPpMhiz8IdRy7To) Log to Intelligence Log node INSERTs into columns workflow_name, session_id, target, summary, generated_at — NONE of which exist in gda_intelligence_log. Every of 22 weekly OODA executions silently fails this write because workflow is in continueOnFail mode. Additionally: unparameterized {{ $(...).first().json.X }} interpolation directly into VALUES — textbook SQL injection vector. | Claude | ⏸️ S-156 | S-155 continuation | Root cause of "intel log broken since S-148" — not ingest, schema mismatch. Fix: rewrite INSERT using canonical columns (source='OODA', agency=target, finding=summary, category='OODA', priority=auto) with $1/$2 parameterization.
RR-28 | Runtime | Medium | intel-feed workflow never executed | GDA.api.intel-feed (KIT8cj4V2cMFdSkA) is active, has correct SQL for gda_intelligence_log, but has never been triggered (0 executions ever). Whatever upstream should invoke it is not doing so. | Claude | ⏸️ S-156 | S-155 continuation | Separate bug from RR-27. Investigation needed: who is SUPPOSED to call this? Cron trigger missing? App.jsx button missing? Orphaned from a removed system?
RR-29 | Process | High | Version history platform-wide gap | n8n_workflow_versions tracking only records partial_update operations. UI edits and full_update calls do NOT create entries. 4 of 5 designated "critical" workflows had ZERO rollback targets at S-155 session start. Systemic rollback protection gap — any workflow edited via UI has none. | Claude | ✅ PARTIAL S-155 | S-155 continuation | Mitigated for 5 critical workflows via forced no-op partial_update (updateName with same name creates a v1). Platform-wide sweep needed: identify all zero-history workflows, force v1 on critical ones. Longer-term: investigate whether n8n config can capture UI edits.
RR-30 | Data Integrity | Medium | aop-tracker hardcoded staleness | GDA.api.aop-tracker Get AOP Data node uses CREATE TABLE IF NOT EXISTS + INSERT ON CONFLICT DO NOTHING to bootstrap gda_aop_tracker with hardcoded values (pipeline_raw=670, pipeline_qualified=435, pipeline_weighted=177). Table is never subsequently updated. Dashboard shows stale-since-creation values as if they were live. | Claude | ⏸️ S-156+ | S-155 continuation | Bigger than Item #4 scope. Fix requires either: (a) dynamic aggregation from gda_opportunity_tracker + gda_capture_plans, or (b) scheduled refresh workflow that UPDATEs the tracker table. Design decision needed.
RR-31 | Cleanup | Low | Misnamed " 2" workflows (rename, don't delete) | GDA.api.opp-tracker 2 (SEJLE89wZa1yfQyB) and GDA.api.ooda-loop 2 (pkPpMhiz8IdRy7To) are LIVE canonical workflows with misleading " 2" suffix. Postgres lookup confirmed NO non-suffixed versions exist (neither active nor inactive). RR-25 flagged them as duplicates — INCORRECT. | Claude | ⏸️ S-156 | S-155 continuation | Rename: strip " 2" suffix via updateName partial_update. The other three (action-items 2, sitrep 2, target-agencies 2) still need validation — possibly also misnamed canonicals.
RR-32 | Performance | Medium | ooda-loop 2 sequential Tavily+postgres pre-work | GDA.api.ooda-loop 2 runs 4 postgres queries (intel, cache, alerts, then Tavily) strictly sequentially before Claude. Tavily is ~8s, postgres combined ~600ms. Could be fan-out/merge parallel for 8s savings (29s → 21s, 28% reduction). | Claude | ⏸️ S-156 | S-155 continuation (analyzed) | Option B from Item #6 analysis. Scoped: restructure Fetch Recent Intel / Fetch Competitor Cache / Fetch Active Alerts / Tavily News Search into parallel branches, merge before Claude OODA Analysis node.
RR-33 | Performance | Medium | daily-actions Claude latency caching opportunity | GDA.api.daily-actions ~93% of 15s latency is Claude API call. Cache output keyed on (date, top_opps_id_list_hash) TTL 1 hour → cache hits return in ~500ms (96% reduction). Cache misses unchanged. Reuses existing gda_dashboard_intel_cache table. | Claude | ⏸️ S-156 | S-155 continuation (analyzed) | Option C from Item #6 analysis. Scoped narrow — only caches when top_opps_id_list hash matches. Any new opp syncs invalidate cache naturally.
--- S-155 CONTINUATION TURN 3 ADDITIONS ---
RR-34 | Process | High | S-155 Switch/If sweep query produced false positives | Sweep query in S-155 kickoff checked n->parameters->options->caseSensitive, which is the node-level options (where fallbackOutput lives). The correct location for Switch nodes is per-rule-condition: n->parameters->rules->values[i]->conditions->options->caseSensitive. The 22 "victims" from the S-155 sweep are a mix of false positives (already-correct workflows like capture-plan and action-history) and real victims (like trends). Cannot safely batch-patch without re-sweeping at the correct path. | Claude | ⏸️ S-156 | S-155 continuation turn 3 | Corrected query captured in S-155 Session Output sheet. Re-run and verify real victim count before any patching. Spot-check: capture-plan = FP, action-history = FP, trends = real victim.
RR-35 | Runtime | Medium | GDA.api.trends Route Action missing caseSensitive+typeValidation | Switch node "Route Action" at typeVersion 3.2. Each rule condition has only leftValue/rightValue/operator — no options key at all. Zero caseSensitive, zero typeValidation, zero version. Same class of bug as S-153 capture-plan and S-154 action-history before their fixes — can cause routes to misfire on case mismatches or type coercion. | Claude | ⏸️ S-156 | S-155 continuation turn 3 (spot-check) | Confirmed real victim via direct MCP fetch. Fix pattern: add options: {caseSensitive: true, typeValidation: "loose", version: 2} to each rule condition. Workflow ID XH3IhyvWMPoZzxBS.
RR-36 | Infrastructure | Medium | Chrome connector MCP reliability | Claude in Chrome javascript_tool/tabs_context_mcp connector dies with 4-minute timeout in ~2 of 3 turns. Recovery only occurs at chat-turn boundary when a new tab group is created. Blocks all SSH-dependent work (postgres queries, bash commands, file grep) for the remainder of the affected turn. | Claude | ⏸️ S-156+ | S-155 continuation turn 3 | Mitigation: verify Chrome responsive at start of each turn needing SSH; pivot to pure-MCP if dead. Investigation for root cause: Claude Desktop MCP bridge persistence config, or alternative SSH paths (direct background tunnel, server-side cron-triggered commands pulled into state).
--- S-155 CLOSE TURN 4 ADDITIONS ---
RR-37 | Runtime | Medium | Format Gist completed + next_steps fields only accept strings (same class as Fix #2) | Discovered during the S-155 end-of-session gist push. GDA.auto.gist-update Format Gist node Fix #2 (shipped earlier in S-155) handled body.broken_blocked as string/array/object/null/undefined. But the same normalize pattern was NOT applied to body.completed and body.next_steps, which continued to accept only strings. When the S-155 close gist push sent arrays to these fields, they rendered as N/A. Follow-through patch applied in S-155 turn 4 with a shared normalize(raw, emptyDefault) helper now handling all three fields identically. | Claude | ✅ SHIPPED S-155 | S-155 turn 4 | Fix #3 applied via n8n_update_partial_workflow updateNode operation. Workflow updatedAt 2026-04-10T19:58:08 UTC. Smoke test BLOCKED by Chrome death — deployment confirmed via MCP workflow fetch but client-side verification could not complete. S-156 turn 1 first-action: re-verify via test payload with arrays in all 3 fields.
RR-36 | Infrastructure | HIGH (bumped from Medium) | Chrome connector MCP reliability — systemic, 75% failure rate | BUMPED to HIGH severity based on S-155 turn 4 evidence: 3 Chrome connector failures in 4 S-155 turns. Pattern is consistent: bare tabs_context_mcp or javascript_tool calls time out at exactly 4 minutes, recovery only at chat-turn boundary. Blocks ALL SSH-dependent work (postgres queries, bash, grep, file reads via SSH webhook) for the remainder of an affected turn. This is not intermittent — it is dominant, and it shrinks the addressable work package of any session by ~50% when it fails. | Claude | ⏸️ S-156+ | S-155 turn 4 severity update | Investigation priorities: (a) Claude Desktop app MCP bridge connection persistence config — is there a heartbeat setting? (b) alternative SSH paths — can a persistent SSH tunnel be established via a different MCP tool? (c) fall-through pattern: retry strategy that avoids 4-minute blocking timeouts and fails fast to pure-MCP mode. Until fixed, every session needs a Chrome pre-flight check at the very start and mid-session health checks before starting any SSH-dependent work block.

## Executive Summary
GDA COMMAND — Platform Maturity Assessment (Final)
Georgetown Defense Analytics ¦ Envision (OU3) ¦ April 6, 2026
Includes: Audit data, Gemini cross-validation, consolidation map, hardening plan, single-operator UX
PLATFORM STATE
148 | 110 | 420+ | $800M+ | 32/32 | 1,230 | 129 | 35
Workflows | Capabilities | Opps Tracked | Pipeline | E2E Pass Rate | Audit Findings | Unauth Webhooks | SQL Injection Risk
SECURITY AUDIT (Real scan — April 6, 2026)
129 unauthenticated webhooks | HIGH | Batch-add X-GDA-Key header auth via MCP
74 workflows with zero error handling | HIGH | Create GDA.error.handler + attach to all
35 SQL queries with unsanitized expressions | HIGH | Parameterize with $1/$2 query parameters
229 SQL queries without query params field | MEDIUM | Audit + parameterize critical ones
n8n v2.9.2 — 6 versions behind | MEDIUM | Update Docker image to v2.14.2
22 unused credentials stored | MEDIUM | Delete to reduce attack surface
89 workflows with excessive data retention | LOW | Configure 30-day execution pruning
GEMINI CROSS-VALIDATION NOTES
Gemini: "43% pass rate" on GDA tests | WRONG. Our E2E tests are 32/32 (100%). Gemini fabricated this metric.
Gemini: "Task Runner node" | PARTIALLY RIGHT. Task Runners are an n8n 2.0 infra config, not a node. But the concept is valid — isolate heavy RAG/doc workflows.
Gemini: "SQL Visualizer" as separate template | REDUNDANT. The Agentic RAG chatbot already does this — AI Agent + Postgres Tool generates charts.
Gemini: "MCP Server Integration" as new add | ALREADY HAVE IT. Our n8n MCP is at mcp.csr-llc.tech. Claude connects every session.
Gemini: "Deep Research Agent" (Template #2883) | VALID ADD. 21,345 views. Autonomous multi-step research via Perplexity. Better than single-shot queries.
Gemini: "Human-in-the-Loop" pattern | VALID ADD. Not a node — its a design pattern. Use Send-and-Wait on Telegram for SITREP/Red Team approvals.
Gemini: "AI Vision scraping" for govt portals | VALID ALTERNATIVE. More resilient than Firecrawl for sites that change layouts. Use Gemini Vision to "read" the page.
FOUR WORK STREAMS
1. HARDEN | Fix 129 unauth webhooks, 35 SQL injections, add error handling, update n8n, configure Task Runners.
2. CONSOLIDATE | Merge fragmented workflows: 6→1 capture, 5→1 comp intel, 10→1 scanners, delete 10 dead workflows.
3. ENHANCE | RSS feeds, PGVector, Telegram bot, email digests, doc auto-indexing, Deep Research agent.
4. GOVERN | Add HITL approval gates on SITREP/Red Team distribution. Formal bid/no-bid approval flow via Telegram.

## Consolidation Map
# | Cluster | Current Workflows | Count | Tab Affected | Problem | Target | Calls Before→After | UX Impact | Priority
1 | Capture Intel | capture-intel, capture-intel-modules, capture-hub, capture-plan, ooda-loop, pwin-calculator | 6 | Capture Plan | 3-4 separate webhooks. Each hits Postgres + Claude independently. 3-4x latency and API cost. | GDA.api.capture-mega | 4→1 | Page loads 60% faster. One spinner instead of four. | HIGH
2 | Comp Intel | competitor-watchlist, comp-intel 2, competitor-threat-score, competitor-field, incumbent-analysis | 5 | Comp Intel | 5 workflows query same competitor data. Each calls Claude separately. | GDA.api.compintel-mega | 3-5→1 | Cards render together. No partial load states. | HIGH
3 | Scanners | broad-opp-search, dept-opp-sweep, on-ramp-scanner, forecast-ingest, dpc-forecast-scraper, dhs-industry-day, golden-dome, amendment-monitor, change-detector, pre-sam-monitor | 10 | Background | 10 independent crons. No coordination. Silent failures. Most have no error handling. | GDA.cron.master-scanner | 10→1 | Reliability: one place to check "did overnight sweep complete?" | HIGH
4 | Opp Data | opp-tracker 2, opp-search, saved-opps, pipeline, launchpad-funnel, opp-classifier | 6 | Pipeline + Launchpad | Frontend calls different endpoints for same data filtered differently. | GDA.api.pipeline-mega | 2-3→1 | Consistent data. No stale cache mismatches between views. | HIGH
5 | Dashboard | dashboard-intel 2, dashboard-intel-deep, ops-dashboard-data, intel-feed, trends, chart-generator | 6 | Dashboard | 6 workflows power one dashboard. Panels load at different speeds. | GDA.api.dashboard-mega (keep SITREP separate) | 5-6→2 | KPIs load as one unit. Faster dashboard render. | MEDIUM
6 | Dead/Superseded | AI Decision Engine [SUPERSEDED], Market Learning [SUPERSEDED], ai-agent 2, general-chat, capture-execution-suite, challenge-ledger, exit-manager, opp-daily, broad-opp-pull, clear-stale-trade | 10 | None | Dead workflows with reachable unauthenticated webhooks. Audit noise. | DELETE all | — | 30+ fewer audit findings. Cleaner instance. | MEDIUM
7 | Documents | doc-ingest, batch.doc-ingest, doc-compare, rag-query | 4 | Doc Ingest | Two ingest versions (single + batch). RAG query separate. | Merge batch into doc-ingest with mode param | Minimal | Cleaner codebase. | LOW
8 | Relationships | relationship-tracker, relationships, contacts, teaming-finder, win-loss-db | 5 | Relationships | 5 CRUD workflows for related data. | GDA.api.relationships-mega | 3→1 | Tab loads faster. | LOW
9 | Financial | aop-tracker, aop-definitions, FY Revenue Calc, nightly-fy-revenue-calc | 4 | Financial Bible | Two revenue calcs (manual + nightly). | Merge aop-tracker + definitions. Keep nightly cron. | 2→1 | Financial tab loads as one unit. | LOW
10 | Dev Utils | grep-appjsx, read-appjsx, ssh-read-file, e2e-test, workflow-mega-test, frontend-e2e | 6 | None | Session-specific test workflows. Overlap. | Keep ssh-read-file. Delete session-specific tests. | — | Less clutter. | LOW

## Gap Analysis
# | Domain | What You Have | WHAT IS MISSING | Impact on You | Solution | Template / Pattern | Priority
1 | Intel Feeds | GovTribe, DPC, DHS/Golden Dome monitors | NO defense news RSS. No real-time SAM.gov. No automated news. | Find out about agency changes days late. Intel is reactive. | RSS Feed Trigger → Claude → email. Apify SAM.gov → webhook. | #5103, Apify SAM.gov | CRITICAL
2 | Semantic Search | RAG query but keyword-only. No vector embeddings. | Cannot search by concept. "Find C5ISR opps" doesnt work. | 420+ opps unsearchable by concept. Connections invisible. | PGVector on existing Postgres. Zero new infrastructure. | #10157 (Agentic RAG) | CRITICAL
3 | SAM.gov Streaming | Pre-SAM monitor INACTIVE. Batch/daily only. | No real-time new opportunity detection. | Competitors with real-time alerts get first-mover advantage. | Apify SAM.gov → webhook. Or SAM.gov API on 15-min cron. | Apify SAM.gov | CRITICAL
4 | Mobile Access | Desktop web only. | NO Telegram bot. No mobile alerts or approvals. | During travel/meetings — GDA is unreachable. | Telegram Bot: private, free, instant. Voice notes → actions. | Telegram patterns | HIGH
5 | Doc Auto-Index | Manual trigger ingest only. | New RFPs sit unindexed in folders. | Drop RFP, forget to ingest, cant query it later. | Google Drive Trigger → chunk → embed into PGVector. | #2753 (94,941 views) | HIGH
6 | Competitor Web | GovTribe data only. No live crawling. | Cannot monitor competitor press, hiring, capabilities. | Miss competitor moves and partnerships. Stale comp intel. | Firecrawl + AI Vision fallback for resilient scraping. | Firecrawl + Vision pattern | HIGH
7 | AI Chat Memory | chat-simple with no persistent memory. | Every chat starts from zero. No multi-tool agent. | Repeat setup every session. AI has amnesia. | AI Agent + Postgres Chat Memory + PGVector + SQL. | #10157, #3414 | HIGH
8 | Deep Research | Predictive intel is single-shot Claude. No multi-step. | Cannot do autonomous deep-dive research on a competitor or program. | Miss nuanced intel that requires following multiple leads. | Deep Research agent pattern: multi-step Perplexity → synthesize. | #2883 (21,345 views) | HIGH
9 | Live Web Research | Static Claude analysis. No real-time search. | Cannot query recent agency/program news during capture. | Capture intel based on stale data. | Perplexity node (core). Nightly per active opp. | Perplexity (core) | MEDIUM
10 | Calendar Sync | No calendar integration. | No auto-created events for due dates or review gates. | Manual deadline tracking. Risk of missed dates. | Google Calendar — auto-create from capture milestones. | Google Calendar (core) | MEDIUM
11 | Email Digests | Daily briefing INACTIVE. | No passive intel delivery. Must log in. | You check or you miss it. | Schedule → Postgres → Claude → HTML → Gmail. | #10776 | MEDIUM
12 | HITL Governance | Red Team and SITREP distribute without approval. | No approval gate before sensitive outputs go to stakeholders. | Risk of distributing AI-generated content without review. | Send-and-Wait on Telegram before distribution. | #2907 (16,049 views) HITL pattern | MEDIUM
13 | Gov Portal Nav | SAM.gov via API only. | Cannot navigate interactive JS-heavy portals. | Some data locked behind interactive portals. | Browserbase + AI Vision fallback. | Browserbase node | LOW
14 | Advanced Docs | No OCR. No scanned PDF handling. | Cannot process scanned RFPs. | Occasional scanned docs require manual work. | PDF Vector — OCR, markdown, AI extraction. | PDF Vector node | LOW

## Templates & Patterns
ID | Template Name | Views | What We Steal | GDA Adaptation | Source | URL
5103 | RSS Feed Analysis w/ AI Risk Scoring | 411 | Daily RSS + webpage → AI risk categorize → HTML email | Morning Briefing: defense RSS → Claude → SITREP email | n8n.io | https://n8n.io/workflows/5103
10157 | Agentic RAG & PGVector (Local Doc Q&A) | 541 | Multi-tool AI: vector + SQL + doc retrieval on Postgres | GDA RAG chatbot: search capture plans + SQL pipeline + SOW retrieval | n8n.io | https://n8n.io/workflows/10157
2883 | Open Deep Research — Autonomous Agent | 21345 | Autonomous multi-step research: search → read → follow leads → synthesize | Deep-dive competitor/program research. Multi-step Perplexity intelligence. | n8n.io | https://n8n.io/workflows/2883
2753 | RAG Chatbot w/ Google Drive & Auto-Embed | 94941 | Drive Trigger → auto-embed docs → vector store → chatbot | Auto-indexing: RFP dropped in Drive → embedded → queryable instantly | n8n.io | https://n8n.io/workflows/2753
2907 | Human-in-the-Loop Email Response | 16049 | AI generates → sends for human approval → distributes after OK | SITREP/Red Team approval: Claude generates → Telegram approve → distribute | n8n.io | https://n8n.io/workflows/2907
3414 | Slack AI Chatbot w/ RAG & Claude | 7366 | Drive → vector store → Claude Agent + memory → chat response | Telegram bot pattern: same architecture, Telegram output instead of Slack | n8n.io | https://n8n.io/workflows/3414
6935 | Contract Renewals & Reminders | 110 | Scheduled → AI notifications → Send-and-Wait approvals | Capture milestone alerting: deadline scan → Telegram with ack | n8n.io | https://n8n.io/workflows/6935
10776 | Daily News w/ AI & Email Reports | 312 | Multi-source RSS → classify → commentary → email | Morning briefing with strategic commentary layer | n8n.io | https://n8n.io/workflows/10776
8497 | Enterprise CLM w/ AI Risk |  | Intake → AI extraction → risk scoring → obligation tracking | Option year alerts, renewal tracking, recompete monitoring | n8n.io | https://n8n.io/workflows/8497
5974 | Pipeline Analytics w/ OpenAI & Sheets |  | CRM query → anomaly detection → alerts → archive | Detect stalled captures, declining PWin, bottleneck opps | n8n.io | https://n8n.io/workflows/5974
2786 | Branded AI Website Chatbot | 88237 | Chat Trigger → Agent → calendar → capture | Embedded chat on gda.csr-llc.tech for natural language Q&A | n8n.io | https://n8n.io/workflows/2786
Apify | SAM.gov Opportunities Monitor |  | Real-time SAM.gov → webhook on new/modified opps | New NAICS matches → webhook → auto-ingest to pipeline | Apify | https://apify.com/m_mamaev/sam-gov-opportunities-monitor

## Master Roadmap
# | Phase | Stream | Action | Closes | What It Does For You | Days | Priority | Status
PHASE 0 — HARDEN (This Week)
1 | P0 | Harden | Batch-add webhook auth (129 endpoints) | Security | Every webhook gets X-GDA-Key header. Closes biggest security hole. | 2 | CRITICAL | ✅ S-133→S-146 (143/143)
2 | P0 | Harden | Unified error handler → 74 workflows | Security | GDA.error.handler catches all failures → Postgres log → Telegram alert. | 3 | CRITICAL | ✅ S-133→S-146 (74/74)
3 | P0 | Harden | Parameterize top 35 SQL queries | Security | Eliminate SQL injection on most exposed queries. | 4 | HIGH | ✅ S-136→S-142 (22 WFs, 32 nodes)
4 | P0 | Harden | Configure Task Runners for heavy workflows | Stability | Isolate 51-node export, 36-node SITREP, RAG into separate containers. | 1 | HIGH | ✅ S-136
5 | P0 | Harden | Update n8n v2.9.2 → v2.14.2 | Security | 6 versions of security patches + performance improvements. | 1 | HIGH | ✅ S-133
6 | P0 | Harden | Delete dead workflows + unused creds | Cleanup | Remove 10 superseded workflows + 22 unused credentials. | 1 | MEDIUM | ✅ S-133
7 | P0 | Harden | Add HITL approval gates (SITREP/Red Team) | Governance | Send-and-Wait on Telegram before distributing AI outputs. | 2 | MEDIUM | ✅ S-137→S-138
8 | P0 | Harden | Configure 30-day execution data pruning | Security | Stop accumulating execution data indefinitely. | 0.5 | LOW | ✅ S-133
PHASE 1 — CONSOLIDATE + FIRST ENHANCEMENTS (Weeks 2-3)
9 | P1 | Consolidate | Merge 10 scanners → master-scanner | Reliability | One cron, one error handler, one completion log. | 3 | HIGH | ✅ S-133
10 | P1 | Consolidate | Merge 6 capture intel → capture-mega | UX Speed | Capture Plan tab: 4 API calls → 1. 60% faster page load. | 4 | HIGH | NOT NEEDED (already merged S-133)
11 | P1 | Consolidate | Merge 5 comp intel → compintel-mega | UX Speed | Comp Intel tab: 5 calls → 1. Cards render together. | 3 | HIGH | NOT NEEDED (already merged S-133)
12 | P1 | Consolidate | Merge 6 opp data → pipeline-mega | UX Speed | Pipeline/Launchpad: 3 calls → 1. Consistent data. | 3 | HIGH | ✅ S-138→S-140 (dashboard-mega)
13 | P1 | Enhance | Morning Intel Briefing (RSS+Claude+Email) | Gap 1,11 | Defense news → Claude classifies → email at 0600. | 3 | CRITICAL | ✅ S-133
14 | P1 | Enhance | SAM.gov Real-Time Scanner | Gap 3 | New NAICS matches in pipeline within 15 minutes. | 4 | CRITICAL | DEFERRED (no SAM API key)
PHASE 2 — FOUNDATION (Weeks 3-4)
15 | P2 | Consolidate | Merge dashboard workflows → dashboard-mega | UX Speed | Dashboard KPIs load as one unit. | 3 | MEDIUM | ✅ S-138 (dashboard-mega)
16 | P2 | Consolidate | Delete 10 dead/superseded workflows | Cleanup | Reduce audit noise by ~30 findings. | 0.5 | MEDIUM | ✅ S-136 (14 WFs deleted)
17 | P2 | Enhance | PGVector Semantic Search | Gap 2 | Search by concept across 420+ opps. On YOUR Postgres. | 5 | CRITICAL | ✅ S-136 (761 vectors, 13MB)
18 | P2 | Enhance | Agentic RAG Chatbot | Gap 2,7 | Multi-tool AI: vector + SQL + docs. Persistent memory. | 7 | HIGH | DEFERRED (Phase 3)
19 | P2 | Enhance | Telegram Bot | Gap 4 | Private bot. "Pipeline health" from phone. Approve bids. | 4 | HIGH | ✅ S-133+S-137 (Telegram bot)
PHASE 3 — EXPANSION (Month 2)
20 | P3 | Enhance | Competitor Crawler (Firecrawl + Vision) | Gap 6 | Weekly crawl of competitor sites. Vision fallback for resilience. | 5 | HIGH | NOT STARTED
21 | P3 | Enhance | Auto-Index Document Pipeline | Gap 5 | RFP in Drive → queryable in 60 seconds. KB grows automatically. | 5 | HIGH | NOT STARTED
22 | P3 | Enhance | Deep Research Agent | Gap 8 | Autonomous multi-step research on competitors/programs. | 4 | HIGH | NOT STARTED
23 | P3 | Enhance | Google Calendar Milestone Sync | Gap 10 | Due dates auto-appear in calendar. Mobile reminders. | 3 | MEDIUM | NOT STARTED
24 | P3 | Enhance | Embedded Chat Widget | Gap 7 | Chat bubble on platform. Ask questions without clicking tabs. | 3 | MEDIUM | NOT STARTED
PHASE 4 — POLISH (Month 2-3)
25 | P4 | Enhance | Perplexity Nightly Research | Gap 9 | Every night: active opps → Perplexity research → Daily Actions. | 4 | MEDIUM | NOT STARTED
26 | P4 | Enhance | Scheduled Email SITREP | Gap 11 | Weekly SITREP auto-emailed. Zero effort. | 3 | MEDIUM | NOT STARTED
27 | P4 | Enhance | Capture Milestone Alerts (Telegram) | Gap 10 | Deadlines within 7/14/30 days → Telegram alerts. | 3 | MEDIUM | NOT STARTED
28 | P4 | Enhance | SMS Critical Failsafe (Twilio) | — | Emergency SMS for critical deadlines. Last-resort. | 2 | MEDIUM | NOT STARTED
29 | P4 | Enhance | n8n Quick-Entry Form | — | Bookmarked URL: drop opp, upload RFP. Mobile-friendly. | 2 | MEDIUM | NOT STARTED
30 | P4 | Harden | Parameterize remaining 229 SQL queries | Security | Full SQL injection hardening. | 5 | MEDIUM | ✅ S-136→S-142 (merged with #3)
PHASE 5 — ADVANCED (Month 3)
31 | P5 | Enhance | Browserbase + Vision Gov Portal Agent | Gap 13 | AI navigates interactive portals. Vision fallback for layout changes. | 5 | LOW | NOT STARTED
32 | P5 | Enhance | PDF Vector Doc Processing | Gap 14 | OCR scanned RFPs. Handle image-heavy docs. | 3 | LOW | NOT STARTED
33 | P5 | Enhance | Autonomous Morning Orchestrator | All | Master loop at 0600: scan → classify → alert → report. | 3 | LOW | NOT STARTED
34 | P5 | Consolidate | Remaining merges (relations, financial, dev utils) | Cleanup | Final cleanup pass. | 4 | LOW | NOT STARTED
S-153 ADDITIONS — SENIOR DEVOPS HARDENING CHARTER
35 | P0 | Harden | Sweep all 152 workflows for queryParams→queryReplacement | Pattern Fix | Eliminates silent postgres v2.5 binding failures across the entire instance | 1 | CRITICAL | IN-FLIGHT S-153
36 | P0 | Harden | Sweep all Auth Check Code nodes for x-gda-key tolerance | Pattern Fix | Standardizes authentication, prevents future workflows from rejecting valid headers | 0.5 | CRITICAL | IN-FLIGHT S-153
37 | P0 | Harden | Defensive options.caseSensitive on all If/Switch nodes | Pattern Fix | Prevents typeVersion 2 crash class documented in WORKFLOW RULES sheet | 0.5 | HIGH | IN-FLIGHT S-153
38 | P0 | Harden | Source attribution audit on all data tables | Compliance | Every record must have source column populated. Per PLATFORM SPECS rule. | 1 | HIGH | IN-FLIGHT S-153
39 | P0 | Harden | End-to-end validation of all user-facing webhooks (24) | Validation | HTTP 200 + persistence proof + source attribution check | 1 | HIGH | IN-FLIGHT S-153
40 | P0 | Harden | Workflow version locks on critical workflows | Regression Prevention | Capture-plan, dashboard-mega, opp-tracker, launchpad-funnel, aop-tracker get versionId pin + rollback procedure | 0.5 | HIGH | IN-FLIGHT S-153
--- S-154 ADDITIONS ---
DevOps S-154 | Pattern sweep for legacy queryParams across all active workflows | ✅ COMPLETE | S-154 | Instance-wide scan complete. Only 6 nodes found. All fixed.
DevOps S-154 | Fix recurring empty-200 regression on predictive-intel and action-history | ✅ COMPLETE | S-154 | Both fixed and verified end-to-end.
DevOps S-154 | Fix cron.pipeline-health-digest (5 layered bugs) | ✅ COMPLETE | S-154 | Wrong table, 3 wrong columns, legacy key. Test row saved.
DevOps S-154 | Corrected platform validation methodology | ✅ COMPLETE | S-154 | R-WR-15 rule. 19/19 (100%) verified against real frontend endpoints.
DevOps S-155+ | Full Auth Check Code node sweep across 151 workflows | PENDING | S-155 | Scan for x-gda-auth-only pattern. 2 fixes found so far (capture-plan + gist-update).
DevOps S-155+ | Full Switch/If node sweep for missing caseSensitive/typeValidation options | PENDING | S-155 | 2 found/fixed so far (action-history Route + capture-plan If). ~20 nodes estimated.
DevOps S-155+ | Wire gda_allocation_m into AOP rollup (aop-tracker workflow) | PENDING | S-155 | Workflow P8AfP8P84xi33auD. S-153 delivered the field, need rollup integration.
DevOps S-155+ | Wire gda_allocation_m into Launchpad Alloc Revenue KPI | PENDING | S-155 | Workflow vaRzM1Jl6HcXjuxs GDA.api.launchpad-funnel.
DevOps S-155+ | Top-strip KPI cards wire to real data (App.jsx lines 5184-5192) | PENDING | S-155 | ORDERS / SALES / EBIT / ROS / FUNDED BACKLOG / BACKLOG currently hardcoded placeholders. R-PS-08 violation.
DevOps S-155+ | gda-daily-actions performance review (15s) | PENDING | S-155 | AI call-driven, functional but slow.
DevOps S-155+ | gda-ooda performance review (29s) | PENDING | S-155 | Tavily + Anthropic + DB sync. Functional but slow.
DevOps S-155+ | Enrich 21 remaining unlinked capture plans | PENDING | S-155 | Most are RS3 TOs not in GovTribe. Need RS3 portal access.
DevOps S-155+ | gda_intelligence_log ingest broken since S-148 | PENDING | S-155 | 3 rows total, 0 last 7 days. Separate from pipeline-health-digest fix.
DevOps S-155+ | Encryption key rotation | PENDING | S-155 | N8N_ENCRYPTION_KEY leaked. Needs n8n stop + env change + restart + re-enter 13 credentials.
DevOps S-155+ | Workflow version pinning + rollback procedure | PENDING | S-155 | 5 critical workflows: capture-plan, dashboard-mega, opp-tracker, launchpad-funnel, aop-tracker.

## Effort Summary
Phase | Timeframe | Harden Days | Consolidate Days | Enhance Days | Total Days | What You Get
Phase 0 | This week | 14.5 | 0 | 0 | 14.5 | All 129 webhooks secured. Error handling on 74 workflows. SQL injection fixed. n8n updated. Task Runners configured. HITL governance gates added.
Phase 1 | Weeks 2-3 | 0 | 13 | 7 | 20 | 4 mega-workflows consolidate 27 old ones. Morning briefing running. SAM.gov scanner live.
Phase 2 | Weeks 3-4 | 0 | 3.5 | 16 | 19.5 | Dashboard consolidated. PGVector semantic search. RAG chatbot. Telegram bot on your phone.
Phase 3 | Month 2 | 0 | 0 | 20 | 20 | Firecrawl competitor monitoring. Auto-indexing docs. Deep Research agent. Calendar sync. Embedded chat.
Phase 4 | Month 2-3 | 5 | 0 | 14 | 19 | Email SITREPs. Milestone alerts. SMS failsafe. Quick-entry form. Remaining SQL hardening.
Phase 5 | Month 3 | 0 | 4 | 11 | 15 | Browser automation. PDF OCR. Autonomous morning loop. Final cleanup.
TOTAL | ~3 months | 19.5 | 20.5 | 68 | 108 | From 148 fragmented workflows → ~100 clean, secure, consolidated workflows. Mobile access. Semantic search. Proactive intelligence. Governed outputs.
COMPLETED (S-136→S-144) | Apr 7, 2026 |  |  |  |  | P0 Harden DONE: SQL param 22WF/32 nodes, Task Runners, HITL gates, dead WF cleanup. P2: Dashboard mega (5→3 API calls), PGVector 761 vectors, Contract Waterfall API. Cron fleet stabilized (~400 errors/day→0). Collation fixed.

## Operator Interface
Channel | When You Use It | What You Can Do | Why This One | Phase
gda.csr-llc.tech (EXISTS) | At desk, deep work | Full platform: all tabs, all AI tools, all charts. This is HQ. | Primary interface. Everything else supplements. | —
Telegram Bot (ADD) | On the move, quick checks, approvals | Text "pipeline health" "CRITICAL deadlines" "run briefing". Voice notes → actions. Approve/reject bids with a tap via Send-and-Wait. | Replaces Slack/Teams/WhatsApp. Free. Private. Works everywhere. Richest messaging API. Also serves as HITL approval channel. | P2
Email Digest (ADD) | Morning with coffee | Morning briefing: new SAM opps, defense news, pipeline changes, deadlines. Weekly SITREP auto-delivered. | Passive intel. Inbox you already check. Zero new apps. | P1+P4
Embedded Chat (ADD) | Already on platform | Natural language Q&A: "What did we submit for IEW&S?" RAG-powered answers from your own data. | For when youre at the computer and want conversational access. | P3
SMS Twilio (ADD) | Emergency only | Receives: "IEW&S due in 24hrs — 2 open items." Thats it. | Last-resort failsafe. Reaches you if you ignore everything else. Pennies/month. | P4
n8n Form (ADD) | Quick mobile data entry | Bookmarked URL → drop opp URL, upload RFP, request capture plan. | Faster than full platform nav for simple submissions. | P4
Slack/Teams/WhatsApp | KILLED | — | Nobody on the other end. Solo operator doesnt need team collab tools. | —

## Current Capabilities
# | Domain | Capability | Workflow | Active | Auth? | Err Handler?
1 | Opp Intel | Opportunity Tracker (420+) | opp-tracker 2 | Y | Y | Y
2 | Opp Intel | Opportunity Search | opp-search | Y | Y | Y
3 | Opp Intel | Saved Opportunities | saved-opps | Y | Y | Y
4 | Opp Intel | GovTribe Feed | govwin-feed | Y | Y | Y
5 | Opp Intel | Broad Opp Search | broad-opp-search | Y | Y | Y
6 | Opp Intel | On-Ramp Scanner | on-ramp-scanner | Y | Y | Y
7 | Opp Intel | Dept Sweep | dept-opp-sweep | Y | Y | Y
8 | Opp Intel | Forecast Ingest | forecast-ingest | Y | Y | Y
9 | Opp Intel | Amendment Monitor | amendment-monitor | Y | Y | Y
10 | Opp Intel | Change Detector | change-detector | Y | Y | Y
11 | Capture | Capture Plan (Shipley v2) | capture-plan | Y | Y | Y
12 | Capture | Auto Capture Plans | auto-capture-plans | Y | Y | Y
13 | Capture | Capture Intelligence | capture-intel | Y | Y | Y
14 | Capture | OODA Loop | ooda-loop 2 | Y | Y | Y
15 | Capture | PWin Calculator | pwin-calculator | Y | Y | Y
16 | Capture | Opp Classifier | opp-classifier | Y | Y | Y
17 | Capture | Stage Promotion | opp-stage-promote | Y | Y | Y
18 | Comp Intel | Competitor Watchlist | competitor-watchlist | Y | Y | Y
19 | Comp Intel | Comp Intel Dashboard | comp-intel 2 | Y | Y | Y
20 | Comp Intel | Threat Score | competitor-threat-score | Y | Y | Y
21 | Comp Intel | Weekly Scan | weekly-comp-scan | Y | Y | Y
22 | Comp Intel | Incumbent Analysis | incumbent-analysis | Y | Y | Y
23 | Proposal | Doc Ingest | doc-ingest | Y | Y | Y
24 | Proposal | Doc Compare | doc-compare | Y | Y | Y
25 | Proposal | RAG Query | rag-query | Y | Y | Y
26 | Proposal | Red Team | red-team | Y | Y | Y
27 | Proposal | Black Hat | black-hat | Y | Y | Y
28 | Proposal | Compliance Matrix | compliance-matrix | Y | Y | Y
29 | Proposal | Clause Library | clause-library | Y | Y | Y
30 | Proposal | Export Engine (51 nodes) | export-engine | Y | Y | Y
31 | Financial | AOP Tracker | aop-tracker | Y | Y | Y
32 | Financial | IDIQ Tracker | idiq-tracker | Y | Y | Y
33 | Financial | FY Revenue Calc | FY Revenue Auto-Calc | Y | Y | Y
34 | AI | Priority Score v2.1 | Priority Score v2.1 | Y | Y | Y
35 | AI | Predictive Intel | predictive-intel | Y | Y | Y
36 | AI | Smart Recommender | Smart Recommender | Y | Y | Y
37 | AI | Pattern Extractor | Pattern Extractor | Y | Y | Y
38 | AI | Daily Actions | daily-actions | Y | Y | Y
39 | AI | Wargame Simulator | wargame | Y | Y | Y
40 | Reporting | SITREP (36 nodes) | sitrep 2 | Y | Y | Y
41 | Reporting | Dashboard Intel | dashboard-intel 2 | Y | Y | Y
42 | Reporting | Chart Generator | chart-generator | Y | Y | Y
43 | Reporting | Intel Feed | intel-feed | Y | Y | Y
44 | Collab | Email Drafter | email-drafter | Y | Y | Y
45 | Collab | Meeting Notes | meeting-notes 2 | Y | Y | Y
46 | Relations | Relationship Tracker | relationship-tracker | Y | Y | Y
47 | Relations | Teaming Finder | teaming-finder | Y | Y | Y
48 | Relations | Win/Loss DB | win-loss-db | Y | Y | Y
49 | Platform | Deploy Pipeline | deploy | Y | Y | Y
50 | Platform | Health Scan | health-scan | Y | Y | Y
51 | Platform | E2E Tests (32/32) | e2e-test suites | Y | Y | Y
52 | Platform | Data Sync v2 | DataSync_v2 | Y | Y | Y
53 | Platform | System Watchdog | System Watchdog | Y | Y | Y
54 | Platform | Chat Simple | chat-simple | Y | Y | Y
55 | Platform | Knowledge Base | knowledge-base | Y | Y | Y
56 | Risk | Risk Intel | risk-intel | Y | Y | Y
57 | Risk | Auto Risk Gen | auto-risk-generation | Y | Y | Y
58 | Risk | Challenge/Exit Monitor | challenge-exit-monitor | Y | Y | Y
59 | Strategic | NDAA/FAR Ingest | ndaa-far-ingest | Y | Y | Y
60 | Strategic | FPDS Enrichment | fpds-enrichment | Y | Y | Y
61 | Notifications | Telegram One-Way Alerts | GDA.notify.telegram | Y | Y | Y
62 | Notifications | Telegram Two-Way Chat | GDA.bot.telegram-chat | Y | Y | Y
63 | Platform Ops | Error Log API | GDA.api.error-log | Y | Y | Y
64 | Platform Ops | Error Log Frontend Viewer | PlatformHealthPage.jsx | Y | N/A | N/A
65 | Platform Ops | MCP Proxy Write Action | GDA.mcp.proxy | Y | Y | N/A